## Weekly Progress Report
MODON - Weekly Progress Report - Construction Projects | [30 empty] | Data Date | 2026-10-19
Contract General Information | [5 empty] | Key Dates | [5 empty] | Cost Summary (SR) | [7 empty] | Performance Summary | [5 empty] | Project Scope
Project Name | Construction of Passenger Station for SAR Railway Sudair Industrial City |  |  |  |  | Contract Award | 2026-03-31 | Contract Award (Hijri) | 10/12/1447 | Revised Completion | 2026-04-07 | Original Contract Value |  | 33090825 |  | O&M Value |  | 0 | EAC | Plan Value | 19.04% | Phys. Plan Value | 38.06% | Quality Score | 88.72% | Civil Work , Storm Water Drainage , Sewer , Portable , Electrical , CCTV
Project ID | SUD1-05-018 |  | Stage | Construction |  | Contract Sign | 2026-03-31 | Contract Sign (Hijri) | 10/12/1447 | Committed Completion | 2027-08-06 | Revised Contract Value |  | 0 | EAC | Revised O&M Value |  | 0 | #REF! | Earn Value | 21.44% | Phys. Earn Value | 26.08% |  | ¢¢¢¢¢ ¢¢¢££
Contractor | Technical Dvelopment Co. "TDC" |  | Status | Active |  | Site Handover | 2026-04-07 | Site Handover (Hijri) | 11/19/1447 | Forecast Completion | 2027-08-06 | Estimate At Completion Value |  | 33090825 | #REF! | Submitted Invoices (Gross Value) |  | 3048399.33 |  | Variance | 2.399% | Variance | -11.98% | Safety Score | 83.33%
Consultant | Saudi Arabia Consulting Engineering Company "EGIS" |  | Modon PM | Engr.Zyad Al Shabat |  | Original Completion | 2027-08-06 | Original Completion (Hijri) | 03/03/1449 | Variance | 0 | Potential Changes |  | 0 |  | Total Deduction |  | -2000 |  | SPI | 1.126 | SPI | 0.68528 |  | ¢¢¢¢¢ ¢¢¢££
Progress Overview
Earned Value Progress (SAR) | [13 empty] | Physical Progress (Effort) | [11 empty] | Earned Value Progress (%)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  | To Date (SAR) | [7 empty] | Budgeted | % Wt. | Weekly Physical Progress |  |  |  | To Date Physical Progress
|  |  |  | Planned | Earned | Original Plan | Cum. Planned | Cum.Earned | Original Plan % | Cum. Planned % | Cum.Earned % | Variance | SPI | (Manhours) |  | Planned | Earned | Plan % | Earned % | Planned | Earned | Plan % | Earned % | Variance | SPI
|  | 0 | 0% | 0 | 0 | 0 | 22585.02 | 0 | 0% | 0% | 0% | 0% |  | 0 | 0% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
Milestones |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 0 | 0% | 0 | 0 | 0% | 0% | 19793 | 19793 | 0% | 0% | 0%
Mobilization |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 19154 | 3% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 31923.4 | 5% | 0 | 0 | 0% | 0% | 32988 | 31339 | 103.3% | 98.17% | -5.165% | 0.95001
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 89385.5 | 14% | 3134 | 4642 | 3.506% | 5.193% | 68347 | 17130 | 76.46% | 19.16% | -57.3% | 0.25063
Construction |  | 33090852 | 100% | 710697.41 | 214091.03 | 0 | 6301807.46 | 7095542.04 | 0% | 19.04% | 21.44% | 2.399% | 1.126 | 478850.8 | 75% | 8552 | 3430 | 1.786% | 0.7163% | 121851 | 98246 | 25.45% | 20.52% | -4.93% | 0.80628
Package-1 |  | 22502032 | 68% | 613731.64 | 214091.03 | 0 | 5886632.12 | 7095542.04 | 0% | 26.16% | 31.53% | 5.372% | 1.2054 | 345775.5 | 54.16% | 8143 | 3430 | 2.355% | 0.992% | 109662 | 98246 | 31.71% | 28.41% | -3.302% | 0.8959
ROAD WORKS 1 |  | 17704263 | 53.5% | 514154.16 | 111822.59 | 0 | 5366361.18 | 6500573.51 | 0% | 30.31% | 36.72% | 6.406% | 1.2114 | 168659.6 | 26.42% | 15867 | 557 | 9.408% | 0.3303% | 73549 | 78905 | 43.61% | 46.78% | 3.176% | 1.0728
ROAD - 01 |  | 10400905 | 31.43% | 275854.68 | 111822.59 | 0 | 3150987.44 | 4140066.18 | 0% | 39.8% | 39.8% | 0% | 1 | 96629.6 | 15.13% | 1058 | 557 | 1.095% | 0.5764% | 58740 | 62660 | 60.79% | 64.85% | 4.057% | 1.0667
ROAD - 02 |  | 7303358 | 22.07% | 238299.48 | 0 |  | 2215373.74 | 2360507.33 | [5 empty] | 72030.1 | 11.28% | 1164 | 0 | 1.616% | 0% | 14810 | 16245 | 20.56% | 22.55% | 1.992% | 1.0969
ELECTRICAL WORKS |  | 3415753 | 10.32% | 62394.6 | 43659.79 |  | 246971.83 | 62629.37 | [5 empty] | 103222.1 | 16.17% | 0 | 0 | 0% | 0% | 18369 | 3751 | 17.8% | 3.634% | -14.16% | 0.2042
MV Network |  | 1577890 | 4.768% | 17205.13 | 0 |  | 35478.52 | 0 | [5 empty] | 37659 | 5.898% | 1036 | 0 | 2.751% | 0% | 1036 | 0 | 2.751% | 0% | -2.751% | 0
Earthing System |  | 4795 | 0.01449% | 0 | 0 |  | 0 | 0 | [5 empty] | 172.8 | 0.02706% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
Street Lighting Network |  | 1454545 | 4.396% |  | 0 |  | 146450.34 | 6382.5 | [5 empty] | 51050.8 | 7.996% | 9986 | 0 | 19.56% | 0% | 13326 | 515 | 26.1% | 1.009% | -25.09% | 0.038646
TELECOMMUNICATIONS WORKS |  | 378522 | 1.144% |  | 43659.79 |  | 65042.96 | 56246.87 | [5 empty] | 14339.6 | 2.246% | 4008 | 2429 | 27.95% | 16.94% | 4008 | 3237 | 27.95% | 22.57% | -5.377% | 0.80763
LOW VOLTAGE |  | 86942 | 0.2627% |  | 0 |  |  | 4926.72 | [5 empty] | 6638.4 | 1.04% | 0 | 329 | 0% | 4.956% | 0 | 651 | 0% | 9.807% | 9.807%
ROAD - 01 |  | 28981 | 0.08758% | 0 | 0 | 0 | 371500.3 | 2028.65 | 0% | 7% | 7% | 0% | 1 | 2072.2 | 0.3246% | 0 | 0 | 0% | 0% | 2336 | 322 | 112.7% | 15.54% | -97.19% | 0.13784
ROAD - 02 |  | 57961 | 0.1752% |  | 869.42 | [8 empty] | 4566.2 | 0.7152% | [5 empty] | 328
PORTABLE WATER |  | 379700 | 1.147% |  | 210420.04 | [8 empty] | 46755 | 7.323%
ROAD - 01 |  | 189850 | 0.5737% |  | -87612.8 | [8 empty] | 20132.1 | 3.153%
ROAD - 02 |  | 189850 | 0.5737% |  | 3809.25 | [8 empty] | 26622.9 | 4.17%
SEWARAGE NETWORK |  | 621335 | 1.878% |  | 20653.36 | [8 empty] | 19751.7 | 3.094%
ROAD - 01 |  | 372801 | 1.127% | [10 empty] | 12694.5 | 1.988%
ROAD - 02 |  | 248534 | 0.7511% | [10 empty] | 7057.2 | 1.105%
STORM WATER |  | 294040 | 0.8886% | [10 empty] | 748.6 | 0.1172%
ROAD N... |  | 294040 | 0.8886% | [10 empty] | 748.6 | 0.1172%
Package-3 |  | 10588820 | 32% | [10 empty] | 133075.3 | 20.84%
Site Works |  | 21090 | 0.06373% | [10 empty] | 1835.5 | 0.2875%
Earthworks |  | 21090 | 0.06373% | [10 empty] | 1835.5 | 0.2875%
Platform Works |  | 6003782 | 18.14% | [10 empty] | 68964.6 | 10.8%
Platform Substructure |  | 5037344 | 15.22% | 0 | 0 | 0 | 371500.3 | 0 | 0% | 0% | 0% | 0% |  | 47410.5 | 7.426% | 0 | 0 | 0% | 0% | 2336 | 0 | 4.927% | 0% | -4.927% | 0
Finishes & Architectural Works |  | 966437 | 2.921% | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  | 21151.7 | 3.313% | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0% | 0%
| Total | 33090825 | 100% | 795259.98 | 214091.03 | 0 | 6301807.46 | 7095542.04 | 0% | 19.04% | 21.44% | 2.399% | 1.126 | 638467.8 | 100% | 11686 | 8072 | 1.83% | 1.264% | 242979 | 166508 | 38.06% | 26.08% | -11.98% | 0.68528
Construction Milestones
[26 empty] | Item No. | Milestones |  | Original (Baseline) | Latest Plan | Forecast | Status | Days Change
[26 empty] | 1 | Project Start Milstone |  | 2026-04-07 | 2026-04-07 | 2026-04-07 | Finish | 0
[25 empty] | #REF! | 2 | Mobilization Finish Milestone |  | 2026-05-06 | 2026-05-06 | 2026-05-06 | Finish | 0
[25 empty] | #REF! | 3 | Work Plan and Timeline Milestone |  | 2026-05-06 | 2026-08-16 | 2026-08-16 | UP | -102
[25 empty] | #REF! | 4 | Completion of MV Work |  | 2027-05-22 | 2027-05-05 | 2027-05-05 | UP | 17
[25 empty] | #REF! | 5 | Completion of road and paving works Milestone |  | 2026-12-06 | 2026-12-31 | 2026-12-31 | UP | -25
[25 empty] | #REF! | 6 | Completion of site and platform work Milestone |  | 2027-07-20 | 2027-08-05 | 2027-08-05 | UP | -16
[6 empty] | 20000000 | [18 empty] | #REF! | 7 | Completion of finishing works and general site works |  | 2027-07-20 | 2027-08-06 | 2027-08-06 | UP | -17
[25 empty] | #REF! | 8 | Engineering Phase Finish Milestone |  | 2026-05-06 | 2026-09-21 | 2026-09-21 | UP | -138
[25 empty] | #REF! | 9 | Procurment Phase Finish Milestone |  | 2027-04-15 | 2027-06-09 | 2027-06-09 | UP | -55
Performance overview
Submittals Status | [10 empty] | Quality | [10 empty] | Safety
Shop Drawings | [10 empty] | Quality Reports | [10 empty] | Safety Statistics | [7 empty] | Proactive Vs Reactive Actions Taken
Item Per WBS |  | Total | Total Submitted Drawings |  |  |  |  | Remaining | Pending | Total Submittals | Quality Reports |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending |  |  |  |  | Category | Item |  | This Week |  | This Month | Year to Date | Cumulative
|  |  | A | B | C | D | Processed | [9 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
Roadwork |  | 90 | 80 | 10 | 0 | 0 | 90 | 0 | 0 | 90 | [11 empty] | General | Total Hours Worked |  | 4280 |  | 9540 | 77050 | 77050 |  |  | Proactive | 42
wet network(sewer,,potable) |  | 47 | 13 | 34 | 0 | 0 | 47 | 0 | 0 | 47 | Non Conformance (NCR) |  | 4 | 4 | 0 | 0 | 0 | - | - | - | - |  | Safe Hours Worked |  | 4280 |  | 9540 | 77050 | 77050 |  |  | Reactive | 0
Telecom |  | 15 | 8 | 7 | 0 | 0 | 15 | 0 | 0 | 15 | Site Instruction (SIR) |  | 0 | 0 | 0 | 0 | - | 0 | 0 | 0 | 0 | Reactive | 0 |  | 0 |  | 0 | 22 | 0
Lighting |  | 28 | 8 | 20 | 0 | 0 | 28 | 0 | 0 | 28 | Material Inspection (MIR) |  | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Electrical |  | 24 | 5 | 19 | 0 | 0 | 24 | 0 | 0 | 24 | Field Inspection (FIR) |  | 152 | 143 | 9 | 0 | 9 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 20 | 0
TOTAL |  | 204 | 114 | 90 | 0 | 0 | 204 | 0 | 0 | 204 | Key Submittals Approval Status | [11 empty] | 0 |  | 0 |  | 0 | 0 | 0
Material Approval | [10 empty] | 1 Quality Plan Approval |  |  | 2026-05-11 |  | 6 Baseline Approval |  |  |  | 2026-08-02 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | Total Hours Worked Vs Safe Hours Worked
Item Per WBS |  | Total | Total Submitted Material |  |  |  |  | Remaining to approve | Pending | Total Submittals | 2 Quality Plan Last Up |  |  | 2026-05-11 |  | 7 No of Approved Version of Schedule |  |  |  | - |  |  | 0 |  | 0 |  | 0 | 0 | 0
|  |  | A | B | C | D | Processed | with Designer |  |  | 3 Safety Plan Approval |  |  | 2026-05-06 |  | 8 Last Approved Schedule |  |  |  | - |  |  | 0 |  | 0 |  | 0 | 0 | 0
Civil /Structural /Architectural |  | 20 | 0 | 18 | 1 | 0 | 19 | 0 | 1 | 20 | 4 Safety Plan Last Up |  |  | 2026-04-30 |  | 9 BOQ Approval Date |  |  |  | - |  |  | 0 |  | 0 |  | 0 | 0 | 0
Electrical |  | 16 | 1 | 13 | 2 | 0 | 16 | 0 | 0 | 16 | 5 Construction Plan Approval |  |  | - |  | 10 No of Approved Version of BOQ |  |  |  | - |  |  | 0 |  | 0 |  | 0 | 0 | 0
Mechanical |  | 7 | 0 | 7 | 0 | 0 | 7 | 0 | 0 | 7 | Invoices Summary | [10 empty] | Proactive | 0 |  | 0 |  | 0 | 0 | 0
[11 empty] | Total Submitted Invoices |  | 2 | Submitted Invoices (SAR) |  |  | 3048399.33 |  | Contract Value (SR) | 0 |  |  | No.of Internal Training |  | 1 |  | 3 | 22 | 22
[11 empty] | PM Approved Invoices |  | 0 | PM Approved Invoices (SAR) |  |  | 0 |  | Planned Value (SR) | 6301807.46 |  |  | No.of Internal Audit |  | 0 |  | 0 | 0 | 0
TOTAL |  | 43 | 1 | 38 | 3 | 0 | 42 | 0 | 1 | 43 | No of Paid Invoices |  | 0 | Paid Invoices (SAR) |  |  | 0 |  | Earned Value (SR) | 7095542.04 |  |  | No. of Toolbox Talks |  | 1 |  | 3 | 20 | 20
Procurement Summary | [10 empty] | No of Pending Invoices |  | 2 | Last Submitted Period |  |  | 0 |  | Submitted (SAR) | 3048399.33 |  |  | Safety Awards/Incentives |  | 0 |  | 0 | 0 | 0
Item Per WBS |  | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Material on Site | Remaining Materials | Material Delivery Completion (Date) |  |  | Advance Payment % |  | 0% | Advance Payment (SAR) |  |  | 0 |  | PM Approved (SAR) | 0 |  | Latest Contract Change Order Log
|  |  | A | B | C | D | Processed |  |  |  | Retention % |  | 0% | Retention (SAR) |  |  | 0 |  | Total Paid (SAR) | 0
Civil /Structural /Architectural |  | 3 | 2 | 2 | 1 | 0 | 3 | - | 0 | 0 | Deduction / Penalties % |  | -0.006044% | Deduction / Penalties (SAR) |  |  | -2000 |  |  |  |  | CCO No. | Date Added | Description of Change |  |  |  |  | Status | Cost | Sch Impact (Months) | Date Approved | Duration
Electrical |  | 18 | 15 | 15 | 3 | 6 | 6 | - | 0 | 0 | Resources at Site
Mechanical |  | 6 | 5 | 5 | 1 | 3 | 3 | - | 0 | 0 | Head Count - Manual |  |  |  | Head Count - Non Manual |  |  |  | Total Head Count |  |  | - | - | - |  |  |  |  | - | - | - | - | -
[11 empty] | Planned | Actual | Next Month Forecast | Saudi Staff | Planned | Actual | Next Month Forecast | Saudi Staff | Total Plan | Total Actual | Variance
[11 empty] | 40 | 65 | 0 | 0 | 20 | 22 | 0 | 3 | 60 | 87 | 27
TOTAL |  | 27 | 22 | 22 | 5 | 9 | 12 | 0 |  |  | Manpower Breakdown by Trade | [6 empty] | Major Equipment
Primavera P6 Schedule Status | [10 empty] | Key Trade | Planned | Actual |  |  |  |  | Type | Planned | Actual | Idle
Project Activities Overview | [10 empty] | Engineer | 2 | 10 |  |  |  |  | Pick Up/Car | 1 | 2 | 0
Schedule Statistics |  |  |  |  | Active Schedule Activities | [5 empty] | Doc. Controller | 1 | 1 |  |  |  |  | Bus | 1 | 2 | 0 | Major Quantity Trackers
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag | 0 | Proc. Team | 1 | 1 |  |  |  |  | Dump Truck | 10 | 12 | 0 | BOQ N0. | Item Description |  |  |  |  | Total Qty | Measu Unit | Plan to Date | Act to Date | Remaining | Variance
855 | 586 | 46 | 223 | 26.08% | 10 | 15 | 0 | 22 | -7 |  | Foreman | 2 | 3 |  |  |  |  | Boom Truck | 0 | 2 | 0 | B1.32 11 13.01 | Subgrade |  |  |  |  | 20530 | m3 | 0 | 15000 | 5530 | 0
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities |  |  |  | Draftman | 1 | 1 |  |  |  |  | Generator | 1 | 1 | 0 | B1.32 11 23.01 | Aggregate base course |  |  |  |  | 16375.94 | m3 | 0 | 9875.94 | 6500 | 0
|  |  | Greater Than 14 Days |  | Less Than 14 Days | [5 empty] | Driver | 5 | 31 |  |  |  |  | CRANE | 0 | 1 | 0 | B1.32 12 16.01 | Asphalt |  |  |  |  | 13360 | m3 | 0 | 573 | 12787 | 0
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag | 0 | UnSkilled Labor | 15 | 20 |  |  |  |  | Showel | 0 | 1 | 0 | B1.32 14 13.13.01 | Interlock |  |  |  |  | 27900 | m2 | 0 | 0 | 27900 | 0
0 | 0 | 0 | 53 | 172 | 598 | 570 | 0 | 2 | -2 |  | Total | 40 | 87 |  |  |  |  | Total | 13 | 21 | 0 | B1.32 16 13.23.01 | Curbstone |  |  |  |  | 20555 | m2 | 0 | 0 | 20555 | 0
Testing And Commissioning | [15 empty] | Top Issues and Risks
Top 5 Issues
Item | Planned Start Date |  | Planned Finish Date |  | Forecast Start Date |  | Forecast Finish Date |  | Actual Start Date |  | Actual Finish Date |  | % Completed | Open Comments | Closed Comments | Issue No | Date Identified | Issue Description |  |  |  | Responsible | Action Taken |  |  | Mitigation |  |  |  |  | Current Status | Expected/Actual Closure | Duration Elapsed
Civil Works | 2027-05-09 |  | 2027-05-31 |  | 2027-06-06 |  | 2027-06-23 | [5 empty] | 0% | 0 | 0 | 3120-11 | 2026-10-03 | Equipment operator found working zone with Non-compalince to site mandatory PPE. |  |  |  | Contractor/HSE Team | it was ensure to wear the mandatory PPE all the time when present on site | [7 empty] | Close | 2 | 1
Storm Water Drainage Network | 2027-01-19 |  | 2027-02-06 |  | 2027-03-18 |  | 2027-04-05 | [5 empty] | 0% | 0 | 0 | 3120-12 | 2026-10-10 | Observe Hot Work activity without proper control measure Fire safety |  |  |  | Contractor/HSE Team | Provide Fire Extinguisher and other requirements as per Hot work requirements. | [7 empty] | Close | 2 | 1
Sewerage Network | 2027-03-14 |  | 2027-03-31 |  | 2027-01-25 |  | 2027-02-13 | [5 empty] | 0% | 0 | 0 | 3120-13 | 2026-10-11 | Observe site without mandatory PPE complaince |  |  |  | Contractor/HSE Team | Wear the mandatory PPE all the time when present on site | [7 empty] | Close | 2 | 1
Portable Water | 2027-03-22 |  | 2027-04-08 |  | 2027-03-28 |  | 2027-04-14 | [5 empty] | 0% | 0 | 0 | 3120-14 | 2026-10-18 | Observe dust created at temporary vehicles roads due insuffient dust control measures. |  |  |  | Contractor/HSE Team | Ensure dust control by regular spraying of water on vehicles routes | [7 empty] | Close | 2 | 1
Electrical Works | 2027-07-18 |  | 2027-08-03 |  | 2027-07-08 |  | 2027-07-26 | [5 empty] | 0% | 0 | 0 | 3120-15 | 2026-10-17 | Observe non complaince of mandatory PPE by equipment operators |  |  |  | Contractor/HSE Team | Wear the mandatory PPE all the time by equipment operators when present on site | [7 empty] | Close | 2 | 1
CCTV Works | 2027-07-22 |  | 2027-08-06 |  | 2027-07-12 |  | 2027-07-27 | [5 empty] | 0% | 0 | 0
0

## General Information
Weekly Progress Report - Construction Projects |  |  | Data Date | 2026-10-19
Contract General Information
Project Name | Construction of Passenger Station for SAR Railway Sudair Industrial City
Project ID | SUD1-05-018
Contractor | Technical Dvelopment Co. "TDC"
Consultant | Saudi Arabia Consulting Engineering Company "EGIS"
Stage | Construction
Status | Active
Modon PM | Engr.Zyad Al Shabat
Key Dates
Contract Award Date | 2026-03-31
Contract Sign Date | 2026-03-31
Site Handover Date | 2026-04-07
Original Completion | 2027-08-06
Contract Award Date (Hijri) | 10/12/1447
Contract Sign Date (Hijri) | 10/12/1447
Site Handover Date (Hijri) | 11/19/1447
Original Completion (Hijri) | 03/03/1449
Revised Completion Date | 2026-04-07
Committed Completion Date | 2027-08-06
Forecast Completion | 2027-08-06
Variance | 0
Key Project Submittals | Submission Date | Days taken to approve orginal plan from site handover date
Quality Plan submission | 2026-04-30 | 23
Quality Plan approval | 2026-05-11
Quality Plan Last Update | 2026-05-11
Safety Plan submission | 2026-04-30 | 23
Safety Plan approval | 2026-05-06
Safety Plan Last Update | 2026-04-30
Risk Management Plan submission | 2026-04-20 | 13
Risk Management Plan approval | 2026-04-30
Risk Management Plan Last Update | 2026-04-30
Baseline Schedule submission | 2026-05-07 | 30
Baseline Schedule approval | 2026-08-02
No of Schedule Versions | -
Last Revised Schedule Approval Date | -
BOQ submission | - | -
BOQ approval | -
No of Approved Version of BOQ | -
Execution Plan submission | 2026-04-30 | 23
Execution Plan Approval | -
Note on D25: AlNuaim, Abdulaziz: As per contract requirments submission of Plans should be 30 days after site handover

## Progress
Project Scope Statement | Construction of Passenger Station for SAR Railway Sudair Industrial City
Earned Value Progress (SAR) | [8 empty] | Physical Progress (Effort)
WBS |  | BOQ Value (SAR) | % Wt. | Weekly (SAR) |  |  | To Date (SAR) |  | Budgeted | % Wt. | Weekly Physical Progress |  | To Date Physical Progress
|  |  |  | Planned | Earned | Original Plan | Planned | Earned | (Manhours) |  | Planned | Earned | Planned | Earned
Milestones | [6 empty] | 0 | 0 | 0 | 0% |  |  | 0 | 0
Mobilization |  | 0 |  |  |  |  | 0 | 0 | 19154 | 3% | 0 | 0 | 19793 | 19793
Engineering |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 31923.4 | 5% | 0 | 0 | 32988 | 31339
Procurement |  | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 89385.5 | 14% | 3134 | 4642 | 68347 | 17130
Construction |  | 33090852 | 100% | 710697.41 | 214091.03 | 0 | 6301807.46 | 7095542.04 | 478850.8 | 75% | 8552 | 3430 | 121851 | 98246
Package-1 |  | 22502032 | 68% | 613731.64 | 214091.03 | 0 | 5886632.12 | 7095542.04 | 345775.5 | 54.16% | 8143 | 3430 | 109662 | 98246
ROAD WORKS 1 |  | 17704263 | 53.5% | 514154.16 | 111822.59 | 0 | 5366361.18 | 6500573.51 | 168659.6 | 26.42% | 15867 | 557 | 73549 | 78905
ROAD - 01 |  | 10400905 | 31.43% | 275854.68 | 111822.59 | 0 | 3150987.44 | 4140066.18 | 96629.6 | 15.13% | 1058 | 557 | 58740 | 62660
ROAD - 02 |  | 7303358 | 22.07% | 238299.48 | 0 |  | 2215373.74 | 2360507.33 | 72030.1 | 11.28% | 1164 | 0 | 14810 | 16245
ELECTRICAL WORKS |  | 3415753 | 10.32% | 62394.6 | 43659.79 |  | 246971.83 | 62629.37 | 103222.1 | 16.17% |  | 0 | 18369 | 3751
MV Network |  | 1577890 | 4.768% | 17205.13 | 0 |  | 35478.52 | 0 | 37659 | 5.898% | 1036 | 0 | 1036 | 0
Earthing System |  | 4795 | 0.01449% | 0 | 0 |  | 0 | 0 | 172.8 | 0.02706% | 0 | 0 | 0 | 0
Street Lighting Network |  | 1454545 | 4.396% | 30727.34 | 0 |  | 146450.34 | 6382.5 | 51050.8 | 7.996% | 9986 | 0 | 13326 | 515
TELECOMMUNICATIONS WORKS |  | 378522 | 1.144% | 14462.12 | 43659.79 |  | 65042.96 | 56246.87 | 14339.6 | 2.246% | 4008 | 2429 | 4008 | 3237
LOW VOLTAGE |  | 86942 | 0.2627% | 0 | 0 |  | 0 | 4926.72 | 6638.4 | 1.04% | 0 | 329 | 0 | 651
ROAD - 01 |  | 28981 | 0.08758% | 0 | 0 |  | 0 | 2028.65 | 2072.2 | 0.3246% | 0 | 0 | 0 | 322
ROAD - 02 |  | 57961 | 0.1752% | 0 | 869.42 |  | 0 | 2898.07 | 4566.2 | 0.7152% | -9146 | 0 | 0 | 328
PORTABLE WATER |  | 379700 | 1.147% | 11904.6 | 210420.04 |  | 66242.45 | 213318.11 | 46755 | 7.323% | 7499 | 4879 | 11285 | 12074
ROAD - 01 |  | 189850 | 0.5737% | 5695.33 | -87612.8 |  | 30835.92 | 121896.06 | 20132.1 | 3.153% | -614 | 2412 | 4746 | 7195
ROAD - 02 |  | 189850 | 0.5737% | 6209.26 | 3809.25 |  | 35406.53 | 91422.05 | 26622.9 | 4.17% | 1179 | 96 | 6539 | 4879
SEWARAGE NETWORK |  | 621335 | 1.878% | 98048.47 | 20653.36 |  | 127245.74 | 108266.16 | 19751.7 | 3.094% | 2570 | 312 | 6304 | 2638
ROAD - 01 |  | 372801 | 1.127% | -32403.53 | 0 |  | 79365.26 | 90221.8 | 12694.5 | 1.988% | 2872 | 1863 | 4447 | 2226
ROAD - 02 |  | 248534 | 0.7511% | -23284.72 | 2122.86 |  | 47880.48 | 18044.36 | 7057.2 | 1.105% | 1723 | 49 | 1857 | 412
STORM WATER |  | 294040 | 0.8886% | 39207.33 | 189906.67 |  | 79810.92 | 205828.17 | 748.6 | 0.1172% | 22 | 38 | 156 | 228
ROAD N... |  | 294040 | 0.8886% | 9801.34 | 36755.03 |  | 79810.92 | 205828.17 | 748.6 | 0.1172% | 22 | 228 | 156 | 228
Package-3 |  | 10588820 | 32% | 96965.76 | 0 |  | 415175.34 | 0 | 133075.3 | 20.84% | 410 | 0 | 12190 | 0
Site Works |  | 21090 | 0.06373% | -297119.56 | 0 |  | 21090.02 | 0 | 1835.5 | 0.2875% | 0 | 0 | 9506 | 0
Earthworks |  | 21090 | 0.06373% | 0 | 0 |  | 21090.02 | 0 | 1835.5 | 0.2875% | 0 | 0 | 9506 | 0
Platform Works |  | 6003782 | 18.14% | 84562.57 | 0 | 0 | 371500.3 | 0 | 68964.6 | 10.8% | 238 | 0 | 2336 | 0
Platform Substructure |  | 5037344 | 15.22% | 84562.57 | 0 | 0 | 371500.3 | 0 | 47410.5 | 7.426% | 2336 | 0 | 2336 | 0
Finishes & Architectural Works |  | 966437 | 2.921% | 0 | 0 |  | 0 | 0 | 21151.7 | 3.313% | 0 | 0 | 0 | 0
Platform Electrical Works |  | 0 | 0% |  |  |  | 0 | 0 | 402.4 | 0.06303% |  |  | 0 | 0
Canopy works |  | 3863605 | 11.68% |  |  |  | 22585.02 | 0 | 33380.9 | 5.228% |  |  | 348 | 0
Civil and Architectural Works |  | 166440 | 0.503% |  |  |  | 11200.01 | 0 | 1830.7 | 0.2867% |  |  | 228 | 0
Metals |  | 3697165 | 11.17% |  |  |  | 11385.01 | 0 | 31550.3 | 4.942% |  |  | 120 | 0
Electrical Works |  | 700343 | 2.116% |  |  |  | 0 | 0 | 28894.3 | 4.526% |  |  | 0 | 0
Low-Voltage Electrical Power Conductors and Cables |  | 36000 | 0.1088% |  |  |  | 0 | 0 | 675.6 | 0.1058% |  |  | 0 | 0
Ondoor Lighting Points |  | 62010 | 0.1874% |  |  |  | 0 | 0 | 389.5 | 0.06101% |  |  | 0 | 0
Outdoor Lighting Fixtures |  | 152490 | 0.4608% |  |  |  | 0 | 0 | 16411.4 | 2.57% |  |  | 0 | 0
CCTV |  | 327218 | 0.9888% |  |  |  | 0 | 0 | 4075.8 | 0.6384% |  |  | 0 | 0
Voice Evacuation System |  | 122624 | 0.3706% |  |  |  | 0 | 0 | 7341.9 | 1.15% |  |  | 0 | 0
Testing and Comissioning |  | 0 | 0% |  |  |  | 0 | 0 | 12737.5 | 1.995% |  |  | 0 | 0
Close Out |  | 0 | 0% |  |  |  | 0 | 0 | 6416.6 | 1.005% |  |  | 0 | 0
Total |  | 33090825 | 100% | 795259.98 | 214091.03 | 0 | 6301807.46 | 7095542.04 | 638467.8 | 100% | 11686 | 8072 | 242979 | 166508
[7 empty] | 19.04% | 21.44% |  |  |  |  | 38.06% | 26.08%
[7 empty] | PW Planned | PW Actuals |  |  |  |  | PW Planned | PW Actuals
[6 empty] | Mobilization | 0 | 0 |  |  | Mobilization |  | 19793 | 19793
[6 empty] | Engineering | 0 | 0 |  |  | Engineering |  | 32988 | 31339
[6 empty] | Procurement | 0 | 0 |  |  | Procurement |  | 65213 | 12488
[6 empty] | Construction | 5591110.05 | 6881451.01 |  |  | Construction |  | 113299 | 94816
[6 empty] | Package-1 | 5272900.48 | 6881451.01 |  |  | Package-1 |  | 101519 | 94816
[6 empty] | ROAD WORKS 1 | 4852207.02 | 6388750.92 |  |  | ROAD WORKS 1 |  | 71328 | 78348
[6 empty] | ROAD - 01 | 2875132.76 | 4028243.59 |  |  | ROAD - 01 |  | 57682 | 62103
[6 empty] | ROAD - 02 | 1977074.26 | 2360507.33 |  |  | ROAD - 02 |  | 13646 | 16245
[6 empty] | ELECTRICAL WORKS | 184577.23 | 18969.58 |  |  | ELECTRICAL WORKS |  | 15603 | 1323
[6 empty] | MV Network | 18273.39 | 0 |  |  | MV Network |  | 542 | 0
[6 empty] | Earthing System | 0 | 0 |  |  | Earthing System |  | 0 | 0
[6 empty] | Street Lighting Network | 115723 | 6382.5 |  |  | Street Lighting Network |  | 11722 | 515
[6 empty] | TELECOMMUNICATIONS WORKS | 50580.84 | 12587.08 |  |  | TELECOMMUNICATIONS WORKS |  | 3340 | 808
[6 empty] | LOW VOLTAGE | 0 | 4926.72 |  |  | LOW VOLTAGE |  | 0 | 651
[6 empty] | ROAD - 01 | 0 | 2028.65 |  |  | ROAD - 01 |  | 0 | 322
[6 empty] | ROAD - 02 | 0 | 2898.07 |  |  | ROAD - 02 |  | 0 | 328
[6 empty] | PORTABLE WATER | 54337.85 | 209508.86 |  |  | PORTABLE WATER |  | 9146 | 11978
[6 empty] | ROAD - 01 | 25140.59 | 121896.06 |  |  | ROAD - 01 |  | 3786 | 7195
[6 empty] | ROAD - 02 | 29197.27 | 87612.8 |  |  | ROAD - 02 |  | 5360 | 4783
[6 empty] | SEWARAGE NETWORK | 111768.79 | 90221.8 |  |  | SEWARAGE NETWORK |  | 5308 | 2326
[6 empty] | ROAD - 01 | 71165.2 | 74300.3 |  |  | ROAD - 01 |  | 3734 | 1963
[6 empty] | ROAD - 02 | 40603.59 | 15921.5 |  |  | ROAD - 02 |  | 1575 | 363
[6 empty] | STORM WATER | 70009.58 | 169073.14 |  |  | STORM WATER |  | 134 | 190
[6 empty] | ROAD N... | 70009.58 | 169073.14 |  |  | ROAD N... |  | 134 | 190
[6 empty] | Package-3 | 318209.58 | 0 |  |  | Package-3 |  | 11780 | 0
[6 empty] | Site Works | 21090.02 | 0 |  |  | Site Works |  | 9506 | 0
[6 empty] | Earthworks | 21090.02 | 0 |  |  | Earthworks |  | 9506 | 0
[6 empty] | Platform Works | 286937.73 | 0 |  |  | Platform Works |  | 2098 | 0
[6 empty] | Platform Substructure | 286937.73 | 0 |  |  | Platform Substructure |  | 2098 | 0
[6 empty] | Finishes & Architectural Works | 0 | 0 |  |  | Finishes & Architectural Works |  | 0 | 0
[6 empty] | Platform Electrical Works | 0 | 0 |  |  | Platform Electrical Works |  | 0 | 0
[6 empty] | Canopy works | 10181.83 | 0 |  |  | Canopy works |  | 175 | 0
[6 empty] | Civil and Architectural Works | 10181.83 | 0 |  |  | Civil and Architectural Works |  | 175 | 0
[6 empty] | Metals | 0 | 0 |  |  | Metals |  | 0 | 0
[6 empty] | Electrical Works | 0 | 0 |  |  | Electrical Works |  | 0 | 0
[6 empty] | Low-Voltage Electrical Power Conductors and Cables | 0 | 0 |  |  | Low-Voltage Electrical Power Conductors and Cables |  | 0 | 0
[6 empty] | Ondoor Lighting Points | 0 | 0 |  |  | Ondoor Lighting Points |  | 0 | 0
[6 empty] | Outdoor Lighting Fixtures | 0 | 0 |  |  | Outdoor Lighting Fixtures |  | 0 | 0
[6 empty] | CCTV | 0 | 0 |  |  | CCTV |  | 0 | 0
[6 empty] | Voice Evacuation System | 0 | 0 |  |  | Voice Evacuation System |  | 0 | 0
[6 empty] | Testing and Comissioning | 0 | 0 |  |  | Testing and Comissioning |  | 0 | 0
[6 empty] | Close Out | 0 | 0 |  |  | Close Out |  | 0 | 0

## Weekly Photos
WEEKLY PROGRESS PHOTOS |  | Data Date | 2026-10-19
Asphalt base course first layer 8 cm at Road 1 | Asphalt base course first layer 8 cm at Road 1
Aggregate Base course layer at Road 1 | Aggregate Base course layer at Road 1
Grading for second layer of subgrade at Road no.1 From st 00+650 to 00+950 | Grading for second layer of subgrade at Road no.1 From st 00+650 to 00+950

## Quality-Stat
Quality -Stat
Quality Reports
Item |  | Issued | Closed | Pending | Avg. Closing (Days) | Pending
[6 empty] | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
Non Conforomance Report (NCR) |  | 4 | 4 | 0 |  |  | - | - | - | -
Site Instruction (SI) |  | 0 | 0 | 0 |  | - | 0 | 0 | 0 | 0
Material Inspection Report (MIR) |  | 15 | 15 | 0 |  | 0 | 0 | 0 | 0 | 0
Field Inspection Request (FIR) |  | 152 | 143 | 9 |  | 9 | 0 | 0 | 0 | 0
Shop Drawings
Item Per WBS |  |  | Total | Total Drawings Submitted |  |  |  |  | Remaining Drawings | Pending | Total Submittals
|  |  |  | A | B | C | D | Processed(A+B+C+D) | with Designer | Submittals With Consultant
Road work |  |  | 90 | 80 | 10 | 0 | 0 | 90 | 0 | 0 | 90
wet network(sewer,potable,Storm) |  |  | 47 | 13 | 34 | 0 | 0 | 47 | 0 | 0 | 47
Telecom |  |  | 15 | 8 | 7 | 0 | 0 | 15 | 0 | 0 | 15
Lighting |  | Mechanical | 28 | 8 | 20 | 0 | 0 | 28 | 0 | 0 | 28
Electrical |  | Electrical | 24 | 5 | 19 | 0 | 0 | 24 | 0 | 0 | 24
TOTAL |  |  | 204 | 114 | 90 | 0 | 0 | 204 | 0 | 0 | 204
Material Approval
Item Per WBS |  |  | Total | Total Materials Submitted |  |  |  |  | Remaining to approve | Pending | Total Submittals
|  |  |  | A | B | C | D | Processed(A+B+C+D) | with Designer | Submittals With Consultant
Civil /Structural /Architectural |  |  | 20 | 0 | 18 | 1 | 0 | 19 | 0 | 1 | 20
Electrical |  | Mechanical | 16 | 1 | 13 | 2 | 0 | 16 | 0 | 0 | 16
Mechanical/STR |  | Electrical | 7 | 0 | 7 | 0 | 0 | 7 | 0 | 0 | 7
TOTAL |  |  | 43 | 1 | 38 | 3 | 0 | 42 | 0 | 1 | 43
Procurement Summary
Item Per WBS |  |  | Total Materials | Total Number of P.O. | Actual P.O. To Date | Remaining P.O | Actual Material on Site | Remaining Materials | Material Delivery Completion (Date)
|  |  |  | A | B | C | D | Processed
Civil /Structural /Architectural |  |  | 3 | 2 | 2 | 1 | 0 | 3 | -
Electrical |  | Electrical | 18 | 15 | 15 | 3 | 6 | 6 | -
Mechanical |  | Electrical | 6 | 5 | 5 | 1 | 3 | 3 | -
TOTAL |  |  | 27 | 22 | 22 | 5 | 9 | 12
Consultant Quality Inspections / Observations (Weekly Basis) | [7 empty] | Overall Average | - |  | Average Closing | -
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Quality Score | Date Closed | Closure Duration |  | This Week Score | - |  | Average Number of Comments Per Audit | -
Note on A38: Malik, Muhammad: This refers to quality observation sheet

## Quality.
QC OBSERVATIONS CHECKLIST
2024-03-26
Project No. |  |  | SUD1-05-018 |  |  | OBS No. | [6 empty] | Inspection Day: |  | 2026-10-19
Project |  |  | Construction of Passenger Station for SAR Railway Sudair Industrial City | [6 empty] | Contractor: Consultant: |  |  | Technical Development Company Egis Engineering cunsultancy
4 |  | Excellent |  | Quality Management System is being practiced and applies to MODON System | [11 empty] | 90 - 100 |  | QC Overall Score | 88.72% |  |  |  |  | 0% | 100 | 0.22883
3 |  | Good |  | Evidence of compliance with plans and procedures. | [11 empty] | 80 - 89 | [7 empty] | 0 | 89 | 0.20366
2 |  | Average |  | Indication level of compliance with standards but there is room for improvement | [11 empty] | 70 - 79 | [8 empty] | 79 | 0.18078
1 |  | Improve |  | Quality and Control is NOT being managed effectively. Needs Improvement | [11 empty] | ≤ 69 | [8 empty] | 69 | 0.15789
0 |  | N/A |  | Item was not applicable or this item was not reviewed during the inspection. | [11 empty] | Zero | [8 empty] | 100 | 0.22883
No. | Topic |  |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) | No. | Topic |  |  |  | E (4) | G (3) | A (2) | I (1) | N/A (0) |  |  |  |  | 437
[6 empty] | 100% | 89% | 79% | 69% | 100% | [5 empty] | 100% | 89% | 79% | 69% | 100% | 88.72%
1 | Control of Access to Site/Office | [5 empty] | 1 |  |  |  | 30 | QC of Excavation |  |  |  | 0 | 1 |  |  | 0 | 0.89 | 0.89 | [6 empty] | Item Count | Score | Distributtion
2 | Document Control Administration | [5 empty] | 1 |  |  |  | 31 | QC of Roads/Round about |  |  |  |  | 1 | 0 |  |  | 0.89 | 0.89 | [8 empty] | Overall | Relevant
3 | Project Documents and Progress | [5 empty] | 1 |  |  |  | 32 | QC of Interlock & Curbstone |  |  |  |  | 1 | 0 |  |  | 0.89 | 0.89 | 4 | 58 | counts |  | 4 | Excellent | 1 | 4 | 1.754% | 2.857%
4 | Contractor's Quality Plan/CM (Updated and Reviewed) |  |  |  |  | 0 | 1 |  |  |  | 33 | Layers/Backfilling Sampling |  |  |  | 0 | 1 | 0 |  | 0 | 0.89 | 0.89 | 3 | 58 | counts |  | 3 | Good | 23 | 69 | 40.35% | 65.71%
5 | MS Log and Paperwork | [5 empty] | 1 | 0 |  |  | 34 | Pump Stations Units | [6 empty] | 0 | 1 | 0.89 | 1 | 2 | 58 | counts |  | 2 | Average | 4 | 8 | 7.018% | 11.43%
6 | RFI, FIR, & MIR Procedure | [5 empty] | 1 |  |  |  | 35 | Quality of Form Work |  |  |  |  | 0 |  | 0 | 0 | 0.89 | 0 | 1 | 58 | counts |  | 1 | Improve | 7 | 7 | 12.28% | 20%
7 | RFI, FIR, & MIR Inventory system | [5 empty] | 1 |  |  |  | 36 | Design Change List | [7 empty] | 1 | 0.89 | 1 | 0 | 58 | counts |  | 0 | N/A | 22 | 0 | 38.6% | -
8 | NCRs Control & Procedure | [5 empty] | 1 | 0 |  |  | 37 | Quality of Concrete Placing |  |  |  |  | 0 | 0 | 0 | 1 | 0.89 | 1 | [5 empty] | Total | 57 | 88 | 100% | 100%
9 | NCR Log | [5 empty] | 1 |  |  |  | 38 | Concrete Surface Finishing |  |  |  |  | 0 | 0 | 0 | 1 | 0.89 | 1
10 | MODON Standard* |  |  |  |  | 0 |  | 1 |  |  | 39 | Pedestals/Columns/Beams Alignment |  |  |  |  | 0 |  |  | 1 | 0.79 | 1 | [6 empty] | Maz Score Available: | 140 | <- Excludes N/A items
11 | Project Risk Plan/Management* | [6 empty] | 0 | 1 |  | 40 | Siporex Lifting & Unloading | [7 empty] | 1 | 0.69 | 1
12 | Monthly Quality Reports* | [5 empty] | 0 | 0 | 1 | 0 | 41 | Siporex Quality Pre-installation | [7 empty] | 1 | 0.69 | 1
13 | ITP | [5 empty] | 0 | 1 |  | 0 | 42 | Siporex Finishing Quality | [7 empty] | 1 | 0.79 | 1 | [5 empty] | Total Score |  | Percentage (%)
14 | MODON Weekly Report | [5 empty] | 0 |  | 1 |  | 43 | Roads / Parking Markings |  |  |  |  | 1 |  |  | 0 | 0.69 | 0.89 |  | 58 |  |  |  | 88 |  | 62.8571 |  | %
15 | Design Change Official Paperwork* | [7 empty] | 0 | 1 | 44 | QC of Finishing Outdoors | [6 empty] | 0 | 1 | 1 | 1 | [5 empty] | Max Score Available | [5 empty] | 31
16 | Design Change was Applied* | [8 empty] | 1 | 45 | Quality of Finishing Indoors | [7 empty] | 1 | 1 | 1 | [5 empty] | 140 | [5 empty] | 32
17 | Material List |  |  |  |  | 0 | 1 |  |  | 0 | 46 | Stairs Quality | [7 empty] | 1 | 0.89 | 1 | [11 empty] | 33
18 | Pending Material Status | [5 empty] | 1 |  |  | 0 | 47 | Tanks Method Statement Work | [5 empty] | 0 | 0 | 1 | 0.89 | 1 | [11 empty] | 34
19 | Lifting Plan* |  |  |  |  | 0 | 0 |  | 1 | 0 | 48 | Electric Rooms | [7 empty] | 1 | 0.69 | 1 | [11 empty] | 35
20 | DWG Log | [6 empty] | 0 | 1 |  | 49 | QC of MCC/ATS Plant Units | [7 empty] | 1 | 0.69 | 1 | [11 empty] | 36
21 | Invoice Status |  |  |  |  | 0 | 0 |  | 1 |  | 50 | Qualified Subcontractor |  |  |  |  | 1 |  |  | 0 | 0.69 | 0.89 | [11 empty] | 37
22 | Site Handover Letter |  |  |  |  | 1 |  |  |  | 0 | 51 | Scaffold/Ladders/Slope/Bridge Compliance | [7 empty] | 1 | 1 | 1 | [11 empty] | 38
23 | Material Testing Results & Certification | [5 empty] | 0 |  | 1 |  | 52 | Protection Applied to Completed Work |  |  |  |  | 0 |  | 0 | 1 | 0.69 | 1
24 | As Build Drawings Status* | [7 empty] | 0 | 1 | 53 | Storage Management in/out Control |  |  |  |  | 0 |  |  | 1 | 1 | 1
25 | Calibrated Lab Tools & Equipment | [5 empty] | 1 |  |  | 0 | 54 | Material Control |  |  |  |  | 1 |  |  | 0 | 0.89 | 0.89
26 | Storage Inventory System | [5 empty] | 1 |  |  | 0 | 55 | Manholes Storing and Quality | [7 empty] | 1 | 0.89 | 1
27 | Logistics Plan | [5 empty] | 1 |  |  | 0 | 56 | Reinforced Steel Quality | [5 empty] | 0 | 0 | 1 | 0.89 | 1
28 | Project Progress Planview | [6 empty] | 1 |  | 0 | 57 | Safety Overview |  |  |  | 0 | 1 |  |  |  | 0.79 | 0.89
29 | Sufficient Number of QC Inspectors | [5 empty] | 0 | 1 |  | 0 | 58 | Waste Management Control |  |  |  | 0 | 1 | 0 |  | 0 | 0.79 | 0.89
0
Score
[8 empty] | *QC % |  |  | 88.72%
Prepared by: |  |  |  | Sarvar Ahmad | [6 empty] | Issued to PM: |  |  | Engr.Zyad Al Shabat
*QC Observations refer only to the practices and documentation observed at time of inspection. The responsibility of the CM and Contractor is to ensure that aspects of Quality are suitably managed. *Scores are a reflection of the general site conditions based upon the findings at the time of the walk through *If Applicable

## HSE-Stat
Safety Statistics
Category | Item |  | This Week | This Month | Year to Date | Cumulative
Category | Total Hours Worked |  | 4280 | 9540 | 77050 | 77050
| Safe Hours Worked |  | 4280 | 9540 | 77050 | 77050
| No.of Internal Training |  | 1 | 3 | 22 | 22
No.of Internal Audit
| No. of Toolbox Talks |  | 1 | 3 | 20 | 20
Safety Awards/Incentives
[7 empty] | Category | Item | This Week | This Month | Year to Date | Cumulative
Consultant Safety Inspection (Weekly Basis) | [6 empty] | Overall Average | 83.33%
Week Number | Date of Audit | Date Issued | Numbers Of Comments | Overall Score | Date Closed | Closure Duration | This Week Score | 83.33%
Week-1 |  |  | 0 | 76% |  | 0
Week-2 |  |  | 0 | 76% |  | 0
Week-3 |  |  | 0 | 83.33% |  | 0
Week-4 |  |  | 0 | 77% |  | 0
Week-5 |  |  | 0 | 83.33% |  | 0
Week-6 |  |  | 0 | 83.33% |  | 0
Week-7 |  |  | 0 | 83.33% |  | 0
Week-8 |  |  | 0 | 83.33% |  | 0
Week-9 |  |  | 0 | 83.33% |  | 0
Week-10 | 2026-08-17 | 2026-08-17 | 0 | 83.33% | 2026-08-17 | 0
Week-11 | 2026-08-24 | 2026-08-24 | 0 | 83.33% | 2026-08-24 | 0
Week-12 | 2026-08-31 | 2026-08-31 | 0 | 83.33% | 2026-08-31 | 0
Week-13 | 2026-09-07 | 2026-09-07 | 0 | 83.33% | 2026-09-07 | 0
Week-14 | 2026-09-14 | 2026-09-14 | 0 | 83.33% | 2026-09-14 | 0
Week-15 | 2026-09-21 | 2026-09-21 | 0 | 83.33% | 2026-09-21 | 0
Week-16 | 2026-09-28 | 2026-09-28 | 0 | 83.33% | 2026-09-28 | 0
Week-17 | 2026-10-05 | 2026-10-05 | 0 | 83.33% | 2026-10-05 | 0
Week-18 | 2026-10-12 | 2026-10-12 | 0 | 83% | 2026-10-12 | 0
Week-19 | 2026-10-19 | 2026-10-19 | 0 | 83% | 2026-10-19 | 0
Week-20 |  |  | 0 | 0% |  | 0
Week-21 |  |  | 0 | 0% |  | 0
Week-22 |  |  | 0 | 0% |  | 0
Week-23 |  |  | 0 | 0% |  | 0
Week-24 |  |  | 0 | 0% |  | 0
Week-25 |  |  | 0 | 0% |  | 0
Week-26 |  |  | 0 | 0% |  | 0
Week-27 |  |  | 0 | 0% |  | 0
Week-28 |  |  | 0 | 0% |  | 0
Week-29 |  |  | 0 | 0% |  | 0

## HSE.
MODON HSE Site Inspection Report
Date |  |  | 2026-10-19 |  |  |  |  | Inspected By: |  |  | Engr Ayman Sabry
Project ID. |  |  | SUD1-02-011 |  |  |  |  | Report No. |  |  |  |  | MODON PM Name |  | Engr.Ziyad Al Shabbat
Project Name: |  |  | Construction of Passenger Station for SAR Railway Sudair Industrial City |  |  |  |  | Contractor: | TECHNICAL DEVELOPMENT CONTRACTING CO. |  |  |  |  | Safety Performance |  | 2 |  |  | 83.33%
Inspections are a snapshot in time and refer only to the practices and documentation observed at the time of the Inspection. It remains the responsibility of the Consultant and Contractor to ensure that all aspects of Health & Safety are suitably managed.
1 |  | Good Practice |  |  | 2 | Need Improvement |  |  |  |  | 3 | Fail (Life Threatening Activity) / Comliance with Plan & Procedures |  | N/A | Atcitty Not Applicable for this Site Inspection Report
No. | Topic | [5 empty] | Wt. | HSE Compliance |  | No. | Topic | [5 empty] | Wt. | HSE Compliance
1 | Access and Egress - (General access to site, segregated from vehicles, / Overhead protection, while entering into the building /Adequate lighting provided when dark or overnight work) | [5 empty] | 5% | 2 |  | 14 | Work at Height - (PPE/Fall Protection(Same level, above and blow) / Training / Fall restraint / competency /Safe access & egress to and from work at height / Ladders / Openings (floor/shafts/Provision of emergency rescue) | [5 empty] | 5% | N/A |  |  |  | 1 | 100 | 1
2 | Traffic Management - (Loading/unloading/sheeting/temp. routes/speed/parking/competence) | [5 empty] | 3% | 2 |  | 15 | Scaffolding - (Temp. Scaffolding Work-platform (All types) - qualified scaffolder / Inspection / Tagged / Safe Access/egress / PTW/Falsework & Formwork) | [5 empty] | 4% | N/A |  |  |  | 2 | 75 | 2
3 | Site Signage - (Project Notice Board & General Signage) | [5 empty] | 2% | 2 |  | 16 | Mobile Elevated Work platform (MEWP) - (PTW/competence requirements/conditions/inspections/tagged/training/Full-body harness) | [5 empty] | 4% | N/A |  |  |  | 3 | 0 | 3
4 | PPE Compliance - (Use, storage, stock, handling & checks - Head, Foot, Eye, Hearing) | [5 empty] | 5% | 2 |  | 17 | Excavation & Trenches - (PTW/Edge protection/buffer zone/Slope/Benching/Shoring/Geo-tech report/Atmospheric hazards/Acess&egress/Emergency management / MS&RA/H.E) | [5 empty] | 3% | 2 | [5 empty] | N/A
5 | Housekeeping - (Material correctly stored/Rubbish cleaned & removed daily/slips & trips hazards) | [5 empty] | 3% | 2 |  | 18 | Confined Space - (PTW/Training/competence/Emergency Management/MS & RA/Safe access/egress) | [5 empty] | 5% | N/A
6 | Storage of Materials - (Transporting, storage, training and use - Combustible / Flammable / Hazardous substances (COSHH) | [6 empty] | 1 |  | 19 | Fire Protection - (Flammable/Oxy. LPG /Combustible separated/FE's/Flashback arrestor/Sparks & slags/Smoking area/PTW/Generators/MS & RA/Emergency Management) | [6 empty] | 1 |  | Red | Serious injury or death (immediately)
7 | Site Waste Management - (Hazardous waste /Combustible waste / Human waste / Construction waste - asphalt, cable, timber, paving roof sheeting tiles, plastic & bricks) | [6 empty] | 1 |  | 20 | Health & Welfare - (Adequate drinking water/shaded - eating & rest area/washing & sanitary facilities/Certified FA/FA Box & Stock/adequate toilets/Ambulance) | [6 empty] | 2 |  | Yellow | Minor or near miss (3 days to comply)
8 | Health Surveillance - (Expose to excessive noise/vibration/dust/silica/CO/cement/radiation/extreme weather condition) | [5 empty] | 3% | 2 |  | 21 | Environmental Incident Measures - (Spill/ Leakage / Concrete wash / vehicle & eqpts. wash / waste disposal/Sewers and drains/emissions/Emergency Management/Training/site run-off water) | [5 empty] | 5% | 2 |  | Green | No issues
9 | Electrical Safety - (Electrical qualified /RCD/GFCI/Industrial Cocket/LOTO/Cable-overhung or buried/Cords in good condition/current inspection tag) | [5 empty] | 5% | 2 |  | 22 | HSE Communications & Meetings - (Schedule HSE Meetings/Safety Committee meetings/Alerts / Lesson learned/Safety Bulletin contains latest HSE KPI) | [5 empty] | 5% | 2
10 | Tools & Equipment - (Includes, powered, hydraulic & pneumatic/Guards in place/Properly stored/RCD Protection/Earthed/Good condition & tagged) | [5 empty] | 3% | 1 |  | 23 | HSE Plan & Associated Procedures - (Approved updated HSE Plan/ CEMP/HAZComm/Procedures/Standards/Project Safety Risk Register) | [5 empty] | 3% | 1 |  | 26 points > 4 minors then is it’s a serious issue
11 | Manual Handling - (Lifting/loading/pulling/pushing/twisting/awkward posture/repetitive task/frequent and prolong physical effort/Reasonable practicable use of mechanical aid) | [5 empty] | 3% | 2 |  | 24 | Health, Safety & Environment Incident reporting - (Review of HSE Statistics, Reporting of Unsafe Act & Conditions/ Reporting of Near Miss incident/Reporting of FA cases/Record MT cases) | [5 empty] | 3% | 1
12 | Vehicle and mobile equipment / Plant - (dumpers; excavators, cranes, piling rigs, grader, roller, loaders/condition/KSA License/certification) | [5 empty] | 5% | 2 |  | 25 | HSE Awareness, Training & Competence - (Policy /Objective & targets/Information, training/Climatic condition awareness/Reponses in emergency situation/ Safety Behavior Observation) | [5 empty] | 4% | 2
13 | Lifting Operations & Rigging - (Lifting Plan/Lifting devices & gears/PTW/Condition/3rd party certification/bank-man/rigger/slingers/man-basket/inspection record/tagged) | [6 empty] | N/A |  | 26 | Project Leadership Site Tours - (Provide evidence of proactive safety performance/Deficient discovered discussed/Positive feedback/Workers resolving safety issues) | [6 empty] | 1
Prepared by: |  |  |  | Abdul kalim | [5 empty] | Sent to MODON PM: |  |  |  | Engr.Ziyad Al Shabbat
Safety Results
1 |  | 7 |  |  |  | 2 |  | 14 |  |  |  | 3 | 0
Note on C13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Safe access / egress for people to their work area 2 - Safe access / egress for construction vehicles 3 - Access properly restricted-site fencing provided and maintained 4 - Access proper and not blocked 5 - Safe access is available for rescue operation 6 - Storage access / exit are clearly marked and unobstructed 8 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 9 - Ensure unauthorized public access is prevented 11 - Site assembled ladders or make-shift tables for access are forbidden on site. 13 - Use proper bridges, walkways or gangways to access or cross trenches or an excavation area 14 - Surrounding areas are cleared and barricaded and access restricted to all unauthorized trades while crane in operation 15 - To ensure early access to accredited medical / rehabilitation services 16 - Parking vehicles on site access roads causing obstruction 17 - All personnel will be instructed that access to firefighting equipment must remain clear at all times 18 - Access control gates to be locked out of hours 19 - Site access gates to be designed and located to, where possible, avoid clashes with external hazards / activities
Note on T13: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Personal Fall Arrest System; 1 - Is the suitable harness harnesses is provided 2 - Are shock absorbing lanyard with 2 locking snap hooks. 3 - Is anchorage point strong enough and can support 5,000 Ibs. 4 - Do inspection checklist is being implemented before use. 5 - Is the emergency plan for rescue in place Personal Fall Restraint System; 1 - The fall restraint equipment should be set and adjusted so there is no free fall over the edge. 2 - A harness or body belt may be used 3 - The anchorage point must support 4 times the intended load. Positioning System; 1 - Is a suitable harness or body belt provided 2 - Is there a not more than 2' free fall maintained 3 - Is the anchorage point capable of supporting 2 times the intended load or 3.000 Ibs, whichever is greater 4 - Is 100% tie-off (protection from falls at all times, even when moving from point to point) provided while using personal fall protection with two lanyards Fall Protection System; 1 - Suitable edge protection and work platforms are to be provided to prevent a fall occurring 2 - Where the provision of edge protection or adequate platforms cannot be provided safety nets or other soft-landing systems such as inflatable bags are to be used to minimize the consequences of a fall. 3 - If nets are used, they must be installed by a competent rigger and fitted as close under the work surface as possible. 4 - Areas below roof works are to be cordoned off and properly signed to prevent personnel being injured from falling materials 5 - If access onto the roof cannot be avoided, edge protection is to be installed 6 - Floor and wall openings are to be protected using covers of adequate strength to withstand the expected load that will be imposed and securely fixed. 7 - Penetrations in walls such as those provided for lift shafts, door openings, etc. are to be closed with suitable strength material or have fixed protective barriers around the penetration with a sign warning personnel of the danger of falling.
Note on C14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are arrival and departure of vehicles and delivery accompany by security department? 2 - Are proper loading, unloading and securing loads, being properly controlled? 3 - Is the proper sheeting & coupling in place when transporting and disposing material to and from site? 4 - Is the parking to the designated parking lot and in reverse order? 5 - Is the designated speed limit adhered on workplace? 6 - Provision of ramps, traffic signs, cones, barriers, demarcation posts and tape, flashing lights and any other traffic control devices. 7 - Do visiting drivers are being inducted at the workplace, prior to enter on the workplace? 8 - Are visiting drivers restricted to dangerous areas, e.g. moving to and from they vehicles to washrooms, lavatory & offices etc.? 9 - Do drivers observe site rules and procedures, for delivery, loading and unloading? 10 - Are the areas wide enough for the safe movement of large vehicles (including visiting vehicles)? 11 - Does drivers are competent, hold valid local driving license and competent training? 12 - Ensure the vehicle and trailers have their brakes applied and all stabilizers properly positioned before beginning loading or unloading?
Note on T14: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Base soundness, load adequately spread (base plate jacks, base plate on firm ground). 2 - Line of standard (vertical) and ledger (horizontal) secure and plumb. 3 - Spacing of transoms on platforms, support for Scaff boards, boards are not over protruded and boards are secured. 4 - Staggering of joints vertical and horizontal. 5 - Guardrail / fall protection. (Top rail – Min.1mtr, Mid rail – 470mm from floor and Toe boards – Minimum150mm) 6 - Longitude and bracing on standards and ledgers. 7 - If close to structure, ties must be on lift below to top working platform and every 3m, load bearing couplers used or tie with certified anchor bolts (eye bolts). 8 - Clamps and tubes used are of correct fittings, size and free from defects. 9 - Tubes & fittings free from defects / deformation. 10 - Safe and proper access available to the working platform. 11 - Scaff tags signed, displayed and up to date. 12 - If close to slab edge/opening scaffold tied and secured to structure correctly.
Note on C15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a Project Notice Board - (showing HSE Statistics / Safety alerts / lesson learned)? 2 - Is there prominent safety boards that are depicting the mandatory PPE on the workplace? 3 - Are other safety required signs are prominently installed on the workplace in relevant to their work-task, as following: > Hazardous Substances - e.g. respiratory protection Sign > Working at Height - e.g. Full body Harness Sign > Working UG - e.g. Full body Harness, SCBA, Ventilation, PTW Signage etc. > Working with Electrical - e.g. Leather Gloves, Goggles, Face shield, Electric shock proof helmet & shoes > Working with Chemicals - Signage = e.g. Impermeable gloves/clothing's, long sleeves, Goggles 4 - General Site Safety Signs: > Prohibition Sign = (e.g., ‘no access for unauthorized persons’). > Warning Signs = (e.g., ‘danger: electricity’) > Mandatory Signs = e.g., ‘eye protection must be worn’) > Emergency Escape or First Aid Sign = e.g., ‘emergency exit/escape route’) > Safety Color Signs = (e.g., yellow means ‘be careful’ or ‘take precautions’) > Illuminated Signs = (e.g., many emergency exit signs) > Acoustic Signals =( e.g., fire alarm) > Fire safety sign > Supplementary Signs = "This way"
Note on T15: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Man-Lift operators are to be competent and trained to operate the specific Man-Lift by examination and hold a current approved certificate / license from an approved and internationally recognized source (TUV, SGS etc. 1 - All Man-Lifts shall be inspected by a 3rd party on an annual basis. 2 - All Man-Lifts shall display a sticker corresponding to the 3rd party inspection certificate. 3 - The manufacturer's instruction manual must be on site for each and every type of Man-Lift in use. 4- A pre-start daily operator inspection of the equipment will be performed and documented on a daily basis as per the manufacturer's instructions. The user is responsible for ensuring this has occurred. 5 - The use of a Man-Lift as, or in lieu of, a Crane is strictly prohibited. Man-Lifts are to be used only for lifting personnel and small tools within the designed Safe Working Load. 6 - The platform is not to be loaded in excess of the designed working load; the safe working load of the platform is to be clearly displayed on both the platform, and body of the equipment. 7 - All persons inside work platforms shall wear a full-body harness attached to the designated anchor point. Personnel must stand on the floor of the working platform; standing on the handrails is strictly prohibited. Harnesses must not be attached to other structures outside of the working platform. 8 - Personnel must stay inside the working platform at all times; the platform must not be used as an access to structures. The use of staging or ladders to extend height is strictly forbidden. 9 - Securing the boom or work platform to any structure is strictly prohibited. The boom or working platform must not be rested upon on any structure, nor is the Man-Lift to be used as a jack/ prop or tie to support other structures. 10 - All Man-Lifts must be equipped with a 5kg (10lb) fire extinguisher. 11 - No man-lifts are to be operated that have had safety devices removed or disabled. Daily operator inspections are to include the testing of these devices (limit switches, alarms and hazard flashing beacons). 12 - Specific Man-Lifts are fitted with outriggers and/or stabilizers which must be used as per manufacturer's instructions. 13 - The work area surrounding the man-lift is to be cordoned off using barricades and signage if the area is used by other workers or vehicles. A full traffic management plan is required for all works involving man-lifts when working on highways. Under no circumstances is any part of a man-lift to extend or swing into a line of traffic.
Note on C16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Does required mandatory PPE (refer specification BS, EN & ANSI) is provided, as following? > Safety helmet (see below for color scheme) > Safety glasses (shaded for outdoor work and clear inside structures and during non-daylight hours) > Safety boots (safety shoes are prohibited) > Orange hi-visibility vest 2 - Additional PPE shall be provided to a specific task 3 - Do specific PPE is provided according to their job requirement? > To work at height - Full Body harness / Fall arrest Devices / Fall Restraint Devices / V & H Lifeline etc. > To work in the confined space - Full Bodyarness, Tripod with retractable lifeline, SCBA, Masks etc. > 4 - Are the PPE stored appropriately to prevent deformation or distortion? 5 - Has self assessment being carried out for in according to the work requirements? 6 - EYEWEAR (Glasses/Goggles/Face Shields) > Eyewear cleaning supplies available. > Safety glasses in good condition and lenses free of scratches. > Goggles adjustment strap not cracked or frayed, not deformed, or lenses not > Face shields in good condition, including adjustment band, and free of scratches or 7 - HEAD PROTECTION > Hard hat bill and suspension attached as allowed by manufacturer. > is pliable, free of dents, cracks, nicks, or any damage due to impact. > Suspension maintained at 1.25 inches from inside of shell. > Suspension free of cuts or fraying, torn headband, adjustment strap workable. > Electrical hard hat matched to hazard classification. > Dated to determine whether within manufacturer’s allowable 5-year use time period. 8 - HAND PROTECTION > Available in sizes matched to employee. > Gloves free of rips tears, abrasions, or holes. > Matched to manufacturer’s specification for chemicals used onsite. > Electrical gloves matched to hazard and periodically inspected for insulating rating. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. 9 - BODY PROTECTION > Available in sizes matched to employee. > Maintained in a clean and sanitary condition, decontaminated or disposed properly. > Vapor-tight fully encapsulated suits tested at required periodic intervals. > Flame-resistant clothing matched to electrical hazard and arc flash rating. > Welding gear matched to degree of hazard and free of cuts, tears or burn holes. > Flotation gear available for work near or on water and in good condition. 10 - HOT AND COLD BODY PROTECTION > Cooling gear available based on degree of heat stress hazard. > Cooling gear in operable, clean, and sanitary condition. > Cold-weather gear provided based on needs assessment. > Cold-weather gear available in sizes to match employees. > Cold-weather gear is in free of tears, rips, or holes and in maintained in a clean condition. 11 - TRAINING > Initial PPE training completed by employees. > Training conducted when new types or styles of PPE are issued. > PPE selection, use, and maintenance reviewed at daily safety briefings. 12 - Provision of impermeable clothing appropriate for the work being performed? 13 - Wearing of shorts, sleeveless shirts, loose clothing are prohibited across the MODON Projects. 14 - Clothing contaminated with grease, oils, fuels and other hazardous substances is not to be worn.
Note on T16: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a valid Excavation PTW in place? 2 - Are spoils, materials, and equipment set back at least 1.5 meters from the edge of the excavation? 3 - Are walkways and bridges over excavations structurally sound, minimum 0.5 meter in width and equipped with standard guard rails and toe boards? 4 - Are warning systems established and used when mobile equipment is operating near the edge of an excavation? 5 - Are employees prohibited from working on the faces of sloped or benched excavations above other employees? 6 - Are the exact locations of Utilities (piping, electrical, etc.) clearly marked? 7 - Are underground installations protected, supported, or removed when an excavation is open? 8 - Are ladders or other means of access and egress in place as per the PTW requirements? 9 - Are all workers within 7.6 meters of a means of access and egress to a trench? 10 - Are ALL ramps constructed of materials of uniform thickness, cleated together, equipped with no-slip surfaces? 11 - Are employees protected from cave-ins when entering or exiting excavation? 12 - Are precautions taken to protect employees from water accumulation and dewatering is being carried out? 13 - Is surface water or runoff diverted after every rainstorm or other hazard-increasing occurrence? 14 - Is the excavation classified as a confined space? If so, is their a valid confined space PTW and is the atmosphere being tested when there is a reasonable possibility of an oxygen-deficient, oxygen-enriched, combustible, toxic, or other harmful contaminant? 15 - Have materials and/or equipment chosen for shoring been based upon soils analysis, trench depth and expected loads (as per Excavation PTW)? 16 - Are shoring materials and equipment that are used for protective systems inspected and in good condition? 17 - Are damaged shoring materials and equipment immediately removed from service? 18 - Are damaged shoring materials and equipment inspected by a Registered Professional Engineer after repairs are made and before being placed back in service? 19 - Are protective systems installed without exposing employees to hazards of cave-ins, collapses, or threat of being struck by materials or equipment? 20 - Are ALL members of support systems securely fastened together to prevent failure? 21 - Are support systems provided to insure stability of adjacent structures, buildings, roadways, sidewalks, etc.? 22 - Are excavations below the level of the base or footing supported, and approved by a Registered Professional Engineer? 23 - Does back-filling progress with the removal of the support system? 24 - Is a shield system installed to prevent lateral movement? 25 - Are employees prohibited from remaining in a shield system during vertical movement?
Note on C17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Sites are to be kept clean and tidy and free from slip, trip and fall hazards. 2 - Do all personnel trained in the importance of good housekeeping, managers, supervisors undertake regular monitoring and inspection of the workplace? 3 - Workplace are to be left clean and tidy at the end of each shift and where there is an accumulation of materials throughout the shift, at regular intervals as required to maintain a clean and safe site. 4 - Buildings under construction and nearing completion must ensure that all combustible and flammable materials are removed at the end of each shift. 5 - Nails are to be removed from timber as soon as possible, where this is not practical they are to be flattened and placed in a safe area (barrier and signs) until nails can be removed at a later time. 6 - Materials are to be stored so as they do not pose a risk to personnel stacking, removing or walking by (further guidance is given in the materials storage and handling section). 7 - All spills are to be cleaned up immediately using absorbent material. 8 - Cables/hoses/other trailing leads are to be protected, buried or secured above head height to avoid a slip trip, fall hazard. 9 - Waste is to be placed in designated containers and covered to protect against high winds, pests or risk of fire. Waste containers are to be emptied on a regular basis to prevent a build-up of material. 10 - Loose or light materials that are stored on roofs or open spaces are to be secured to prevent them from inclement weather. Location: 1 - Receptacles located inside buildings shall be kept at least 18 inches away from combustible walls and partitions. 2 - Receptacles for combustible trash that are located outside of buildings shall be placed at least 15 feet from the building or combustible material. Use: 1 - Cigarettes, cigar butts, matches, and similar potential ignition sources should never be placed in a trash receptacle. Proper receptacles for such items should be provided in areas designated for smoking. 2 - Broken glass, empty jars, scrap metal, and similar construction material should never be placed in office trash containers. A roll-off bin or other appropriate container should be used to hold construction debris. Environmental: 1 - Container storage areas shall be kept clean and free of trash. Improper disposal of food waste can attract pests and vermin. Prevention methods that do not involve the use of toxic chemicals is the preferred method of pest control. 2 - Outdoor containers should be kept covered when not in use so as to avoid attracting pests and to prevent the entry of water. Dripping or leaking trash containers may violate local storm water quality discharge regulations. 3 - Promote recycling by contracting with a waste removal company that provides reuse as part of the waste processing or by providing segregated bins for the collection of office paper, aluminum cans, plastic bottles, and toner cartridges. Rinse empty cans and bottles of sugar-based soda so as not to attract ants and other pests. 4 - Proper lighting (indoor) or during Night Shift are provided. Accurately installed. No impairement or poor visibilty is generated. No shadow due to installation of lights are presents.
Note on T17: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Permit is taken for confined space entry and all recommended precautions are in place. 2 - Operatives are trained and fit for the specified job. 3 - Confined space is well ventilated by means of mechanical ventilation. (Exhaust fan, blowers, low velocity air hose etc.). 4 - Rescue system (Tripod with hoisting device, Rescue Harness etc.) in place and sufficient trained persons are available for the rescue operation. 5 - Safe access is available for rescue operation. (Manhole size - Min. 450 mm X 407 mm or 457 mm Dia.) 6 - Atmospheric monitoring conducted and confined space is safe to enter. Percentage of gas concentration will be monitored and recorded every 4 hrs. A. Oxygen percentage. (Permissible limit – 19.5% to 23.5%) B. Flammable gas or vapors.(Permissible limit - <10% of LFL) C. Carbon Monoxide. (Permissible limit - <50ppm) D. Hydrogen sulfide.(Permissible limit - <10ppm) E. Any other toxic gas or vapors. _______________________________ 7 - Minimum two persons shall be assigned to work in the confined space. One person will remain in the entrance at all times to monitor the work 8 - All persons shall wear safety harness, which should be connected to safety line from outside at all times. 9 - All electrical equipment & leads are free from damage and guards in place. 10 - All electrical tools & equipment are connected through ELCB. 11 - Compressed gas cylinders are kept outside the confined space. 12 - supervisor / Foreman will be available at all time to monitor the work and for the rescue operation. 13 - Tool box talk conducted for the entire team and they are well aware of the risks. 14 - Proper communication system is available in between persons inside and standby person. 15 - Trained First aider with first aid kit will be available when working in the confined space. 16 - Confined space entry register is available and shift records will be maintained. -
Note on C18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Combustible: 1 - Ensure oily rags, combustible material and other flammable substances which may ignite are not accumulated and that they are removed without delay to the designated disposal / storage area. 2 - Combustible materials shall not be stored within 20 feet (6.1 meters) of compressed gas cylinders. 3 - Safety cans used for dispensing combustible liquids shall be kept at a point of use 4 - Storage rooms for combustible liquids must have explosion-proof light fixtures 5 - No flames - hot work or smoking is be permitted in combustible liquid storage areas. Flammable: 1 - Adequate training in the use and storage of flammable liquids is in place. 2 - Storage of Flammable liquids in accordance with NFPA approved flammable storage lockers or in low value structures at least 50 feet from any other structure. 3 - Do not store other combustible materials near flammable storage areas 4 - Bulk drums of flammable liquids must be grounded and bonded to containers during dispensing 5 - Portable containers of gasoline or diesel are not to exceed 5 gallons 6 - Safety cans used for dispensing flammable liquids shall be kept at a point of use 7 - Appropriate fire extinguishers are to be mounted within 75 feet of outside areas containing flammable liquids, and within 10 feet of any inside storage area for such materials. 8 - Storage rooms for flammable liquids must have explosion-proof light fixtures 9 - No flames - hot work or smoking is be permitted in flammable or combustible liquid storage areas. 10 - Flammable liquid transfer areas are to be separated from other operations by distance or by construction having proper fire resistance. 11 - When not in use flammable liquids shall be kept in covered containers. 12 - Flammable materials are considered hazardous and as such, material safety data sheets and appropriate hazard communication training for affected employees is required 13 - Maintain high levels of housekeeping, particularly with relations to flammable materials. 14 - Where flammable materials are handled in the course of work, safe work procedures must be prepared and documented with reference made to the Material Safety Data Sheets (MSDS‘s) for the materials concerned. 15 - All people handling, working with or in control of flammable substances must be properly trained and supervised (documentation to be maintained). 16 - Lead, dust, fumes and vapor constitute a major health hazard to workers. Hazardous Substances COSHH 1 - Under COSHH the risk presented by any hazardous substance assessed using hierarchy of control, stored, transported, created or disposed and usage at the workplace; > Very toxic or toxic: Substances that, in low quantities, cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Harmful: Substances that may cause death or acute or chronic damage to health when inhaled, swallowed or absorbed via the skin > Corrosive: Substances that may, on contact with living tissues, destroy them > inhalation into the lungs, when the substance is in the form of a gas, vapor, fume, mist, aerosol or dust > absorption through the skin or eyes by contact with a substance that can penetrate unbroken skin, or is absorbed through unprotected cuts or grazes > injection by contact with contaminated sharp objects or high-pressure equipment, e.g. water jetting > ingestion by swallowing particles of a hazardous substance resulting from hand-to- mouth transfer
Note on T18: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are regular and frequent fire safety inspections carried out? 2 - Have a sufficient number of fire marshals/evacuation officers been appointed? 3 - Are water supplies adequate? 4 - Does the building or site have a written fire procedure? 5 - Is there an effective permit to work system in operation for all hot work and other fire related work? 6 - Do all doors from areas from which a large number of people may have to escape open in the direction of travel? 7 - Do all emergency exit doors (i.e. doors not in normal use) have clear instructions displayed on how to open? 8 - Are all escape routes clear and unobstructed? 9 - Are all fire exit doors correctly signed? 10 - Is all fire fighting equipment immediately visible or correctly signed? 11 - Are all flammable and explosive substances adequately signed to indicate their presence and danger? 12 - Where necessary, is there a sufficient number of emergency lights to adequately illuminate all internal escape routes, exit doors and signs? 13 - Where automatic fire detection is deemed to be necessary is there an adequate number of detectors in the critical areas? 14 - Where the means of raising the alarm is by hand-operated devices, can the operation of one device be heard throughout the entire building or site? 15 - Is there an adequate number of fire extinguishers in the building? 16 - Is there firefighting equipment other than extinguishers in the building? 17 - Are all electrical circuits and fixed electrical installations examined and tested at an acceptable frequency? 18 - Is housekeeping to an acceptable standard? 19 - Have all staff been trained in fire procedures in the last twelve months? 20 - Are all fire drills adequately recorded?
Note on C19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - General construction waste streams generated including; > Asphalt, cable, timber, paving, roof sheeting, tiles, plastic sheeting and brickwork. > Excess concrete, spoil material from excavations. > General waste, such as putrescible food scraps and packaging from workers. > General (food) waste, construction/concrete waste, hazardous waste, paper/cardboard and waste water/sewage. 2 - Are hazardous waste identified with hazardous Waste label. 3 - Containers are properly labeled in according to their contents. 4 - Container inspections are documented in writing using the Container Inspection Checklist. 5 - Weekly inspections logged into book using the Accumulation Area Inspection Log Sheet. “NO SMOKING OR OPEN FLAME” sign posted. 6 Disposal facilities identified, evaluated using the procedures. 7 - Disposal facility accepted waste and issue approval letter. 8 - Waste transfer/dispose tracked using Waste Tracking Form. 9 - Waste streams, such as asphalt and concrete, to be recycled should be segregated and separately stored. 10 - Spill Release Contingency: 1 - Prior to beginning operations, ensure that on-site spill response capabilities (containment and personal protective equipment) are consistent with task requirements described in job hazard analysis.
Note on T19: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: HHE is required at all locations where chemical hazards exist, such as; storing, transferring and handling facilities, under routine conditions. The HHE scope shall include the physical, chemical, radiological, and biological health hazards. Physical health hazards include elevated noise and vibration exposures, repetitive motion work operations, ionizing and non-ionizing radiation exposures heat and cold stress and biological hazards include infectious disease agents. HHE shall be performed before the site mobilization; 1 - Is the adequate eating or mess area is provided and sufficient for number of workers? 2 - Are sufficient tables and Chair are provide and Kept Clean? 3 - Are FEs, signs, pest control being implemented? 4 - Is washing Area sufficient and Kept Clean? 5- Cooking Area Kept Clean? 6 - L.P.G. Cylinder stored outside, secured & upright 7 - Sufficient drinking water provided. Filters changed (as per manufacturer recommendation)? 8 - Sufficient toilets, washbasins, cleaned/disinfectant provided? 9 - Provision of First Aider 10 - Provision of Nurse 11 - Provision of First Aid Kit 12 - Provision of site clinic with required first aid equipment and items. 13 - Provision of shaded area on the workplace 14 - Provision of Ambulance or an equal arrangement in place" 15 - Smoking area is Prohibited other than designated smoking areas, clear of flammable and combustible materials? 16 - All toilets, washing, rest and eating facilities to be kept clean, hygienic and be well maintained at all times? 17 - Waste Management - Covered bins, emptied daily, close proximity, color coded etc.? 18 - Are the monitoring, including integrated air sampling, noise dosimetry and other exposure assessments, being carried out? 19 - Are the Physical, chemical, and biological stresses, being identified, results are taken with action level to prevent sickness, impaired health, significant discomfort, or inefficiency in workers? 20 - Are WEL, LEL, OEL PEL & TLV linked to control workers airborne exposure to a chemical in a concentration above which is likely to cause death or immediate or delayed permanent adverse health effects or prevent escape from such an environment, if bening implemented?
Note on C20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Is the hierarchy of Control is beng carried out on the following and recorded; 1 - Exposure to Chemical; e.g. - Dust, Gas, Mist, Vapor 2 - Exposure to Radiation; e.g. - Pipe radiography etc. 3 - Exposure to Biological Hazard; e.g. - Bloodborne pathogens / Legionella / Leptospirosis 4 - Exposure to noise; e.g. Loss of hearing / Physical damage to hearing mechanism 5 - Heat and cold stress work; e.g. - Heat-stroke, Heat stress / Frostbite / 6 - Repetitive Motion Work; e.g. - Musculoskeletal disorder, awkward position etc. 7 - Is the risk assessment carried out on the hazardous material and covering the following; > Allowable exposure limits, > Exposure monitoring requirements, > Methods of compliance for potential over exposure conditions, > Medical surveillance program, > Hazard communication, employee training requirements, 8- Is the IH Surveillance Plan should being implemented and have rocored on the following; > Which exposure groups require IH monitoring and medical surveillance > Specific substances or agents to be monitored, > The OELs to be used to evaluate results > The statistical basis to continue or cease monitoring > Specific medical testing/protocol to be implemented 9 - Do we've program on identifies work conditions such as the following, the exposure must first be mitigated or work shall not be performed. > Oxygen concentrations less than 19.5% or greater than 23.5%, or > Atmospheres greater than 1% of the Lower Explosive Limit, or > Atmospheres that are >50% of Immediately Dangerous to Life or Health (IDLH) concentrations, or > Work with sensitizers or known human carcinogens, mutagens, or teratogens without process isolation or fully encapsulating personal protection, or > Work with highly infectious biological agents without process isolation
Note on T20: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Are all dispensing areas diked or properly graded to control drainage of spilled fuel? 2 - are all workers and operatives are trained to use spill response kit? 3 - Is the procedure in place for collecting and/or containing, and disposing of spilled materials? 4 - All tanks & vessels areas are diked to contain accidental spills?. 5 - Do measures taken to prevent an accidental contaminated runoff from construction , operation, maintenance, plant and storage areas? 6 - Do measures taken to control on deposits of oils, greases and fuels, from site plant and vehicle operations, mechanical failures, spillages and discharges to ground or drains and the dispersion of unattended spills by plant / vehicle movements?. 7 - Do measures taken to control on fuels, oils and other hazardous chemicals spilled on site during re-fueling, storage or transport operations?. 8 - Do we have an Emergency Response Procedure will be followed in the event of environmental emergency such as an oil or chemical spill? 9 - Is there a procedure for concrete wash, clean and dispose to prevent ground contamination, such as; Concrete wash pits with leak proof sedimentation tanks will be provided for washing concrete mixer trucks. The design and location of such wash pits shall be agreed with the Project Manager prior to its construction on site. Concrete dumping or spillages of any kind shall not be allowed in any other location on site? 10 - Is there a procedure to used in the situation of a major spills that will have an impact on the surrounding environment will be promptly reported to the Fire Brigade? 11 - Are there a procedure of disposing off any damage/leakage drums or containers shall be removed in accordance with the local requirements? 12 - Are there a procedure of dealing with spilled contaminated soils, resulted and remediated, accordingly? 13 - Are all personnel trained in the use of spill procedure and response and the adequate spill kits are available on site?
Note on C21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - All electrical extension cords are equipped with nonconductive plugs 2 - Cords must not be spliced or draped over nails, metal objects 3 - The use of extension cords by means of multiple outlet plugs from single outlets is prohibited 4 - All electrical service removals, alterations and equipment installations are performed by an authorized electrician 5 - Faulty electrical installation 6 - Electrical supply disruption 7 - Exposed cables 8 - Trip / fall hazards from installed cables 9 - Fire hazard Electrical overload 10 - electrocution 11 - Electrical (short circuit) - Contact with exposed conductors or a device that is incorrectly or inadvertently grounded, such as when a metal ladder comes into contact with power lines 12 - Electrical - (static discharge) 13 - Electrical Fire - Use of electrical power that results in electrical overheating or arcing to the point of combustion or ignition of flammables, or electrical component damage 14 - Improper grounding 15 - Damaged insulation 16 - Exposed electrical parts 17 - Overloaded circuits 18 - Inadequate wiring 19 - Wet conditions 20 - Overhead power lines 21 - Damaged tools and equipment
Note on T21: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a meaningful and an effective consultation and communication on health and safety matters being implemented through out the project? 2 - Is the Consultation and communication on health and safety matters in place through the following mechanisms: > Project specific induction - (prior to commencement of contracted work) > Work activity Induction (in SWMS or equivalent) - (prior to commencement any construction work) > Toolbox Meetings - (Monthly intervals or generally when there is the introduction of a new process (SWMS) or when discussing OHS issues/topics). > Subcontractor Meetings - (weekly) > Project team meetings - (weekly) > HSE Committee Meeting - (as agreed with the HSE Committee) > OHS Report - (monthly) > Project Notice Board and general signage - (as required) 3 - Is there a method of communication is to be established in the work procedures to allow constant monitoring of those persons working in the confined space? 4 - Is there a material safety data sheets and appropriate hazard communication training for affected employees is in place? 5 - Are all environmental aspects and impacts been communicated to employees? 6 - Dose the notice
Note on C22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1- Check that all the workers are using safe hand tools/power tools and instruct them to operate and maintain the same in safe manner 2 - Ensure power tools and hand tools are checked prior to issue 3 - Damaged tools and equipment 4 - Electrical tools or electrical equipment are not to be issued for use until inspected. 5 - Electrical tools or electrical equipment are not to be issued for use until inspected. 6 - "Defective" electrical tools and equipment are to be tagged and removed from service until repaired and inspected 7 - The frequency for inspection of construction electrical tools and electrical equipment shall be monthly and inspection indicated by attached color-coded tape or color- coded tie wraps and a color coded inspection tag with Contractor‘s name, the supervisor, the inspection date, equipment number and signature of competent inspector displayed on the tag. 8 - Checking the cords for worn or cracked insulation. 9 - Checking the cords entry to plug and tool housing for frayed or worn insulation and strain relief. 10 - Checking the plug prongs for damage. 11 - Checking the plug for exposed connectors 12 - Checking the equipment housing for damage. 13 - Checking trigger locks to ensure they have been removed 14 - Checking the leads for signs of wear, poor connections at probes, etc. 15 - Checking the housing and the readout window for cracks, loose screws, etc. 16 - Check all Ground Fault Circuit Interrupters (GFCI) during the monthly inspections. 17 - Machines are free from any defects / damage. 18 - Pressure switch and safety guards in place where applicable. 19 - Leads are fitted with correct plugs & sockets and free from damages. 20 - Leads wires are free from joints, cuts and other defects. 21 - Leads are suitably rated for the electric current. 22 - Machines / Tools are equipped with properly functioning dead man switch. 23 - Tools issue and maintenance record is properly maintained. 24 - Tools are correctly stored. 25 - Discarded Tools / cords are marked and stored separately.
Note on T22: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is the Project HSE Plan presents actions, responsibilities, protocol, conformance, verification and containment activities to be undertaken by project staff and sub-contractors at all times during the construction phase of the project. 2 - Is the implementation of the HSE plan is being monitored, evaluated for accuracy and any changes made communicated to all relevant personnel. 3 - Is the HSE Plan, CEMP, Security Plan, HAZcomm., standards & procedures are updated, signed, approved and distributed, acknowledged to the construction team's responsible individuals? 4 -Is the project overall safety risk register developed, approved and being implemented?
Note on C23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: Immediate Postural and Load Factor; 1- Is the body position stable? 2 - Is the trunk of the body straight (not twisted)? 3 - Is the operation carried out by one person? 4 - Is the load kept close to the body? 5 - Can the handler avoid stretching upwards? 6 - Can the handler avoid a prolonged period in one posture? 7 - Can the handler perform the task without overreaching? 8 - Are both hands used for grasping? 9 - Are the hands less than a shoulder width apart? 10 - Is the load positioned centrally in front of the body? 11 - Is the load reasonably symmetrical? 12 - Is the load stable and easy to grasp? 13 - Can handlers move and position themselves freely? Environmental Risk Factor; 1 - Too hot? 2 - Too cold? 3 - Too bright? 4 - Too dark? 5 - Too noisy to allow effective communication? 6 - Too wet? 7 - Slippery underfoot? 8 - Does any personal protective equipment interfere with the task? Carrying; 1 - Is the load carried at knuckle height? 2 - Is the load carried at arm's length from the body? 3 - Is the load carried for more than 10 meters? Seated Work; 1 - Is the load lifted from below thigh height? 2 - Is the load lifted to above shoulder height? 3 - Is the load lifted at arm's length from the body? 4 - Does the handler have to twist significantly to the side? 5 - Is the load heavier than 5kg? Pushing and Pulling; 1 - Does the pushing and pulling take place below knuckle height? 2 - Does the pushing and pulling take place above shoulder height? 3 - Is the initial or maximum force required to push or pull the load more than 25kg? 4 - Is the continuous force required to keep the load in motion more than 10kg?
Note on T23: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there a system of proper HSE reporting in place, such as; all work-related incidents including near misses, injuries, illnesses, property damage, environmental incidents, security events and motor vehicle incidents, using proper protocol followed? 2 - Is the HSE incidents, accident, near misses, unsafe acts/conditions and dangerous occurrences are being reporting in timely manner and in the approved company format? 3 - Are the workers informed, trained in reporting all near misses, unsafe acts/conditions to the appropriate authority or line of manager? 4 - Is the Weekly / Monthly HSE Statistics data, including (leading & lagging) indicators, reviewed by the senior management?
Note on C24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: CHECKS; 1 - Plant guarding is in place and in good condition to prevent injury from parts disintegrating or failing 2 - Access and egress is in good condition, hand holds, ladder etc. are sound and in place 3 - Operator's seat and controls are in good condition and all safety devices (limiters and indicators) are labelled and fully operational. 4 - Operator's manual / instructions supplied by the manufacturer of the plant are available in the plant. 5 - Hazards with the use of the plant are identified, i.e. Safe working limits on batters, operator safety instructions etc., are displayed clearly in the cabin of the plant for operator reference. I.E. PLANT SPECIFIC RISK ASSESSMENT. 6 - Hazard controls, i.e. seat belts must be worn and hearing protection must be worn, caution/danger signs (counter weight slewing area, excavators and cranes) etc. are displayed in the cabin or on the plant in a position relevant to the hazard. 7 - Operator cabin/work platform access is clean and free of debris, loose tools, equipment, grease oil and is in an orderly condition. 8 - Plant is clean and free from oil leaks and oil build up. 9 - Plant Pre Start inspection is complete and a record of the inspection will be provided at commencement on the site. 10 - Certification of operator / proof of competency. 11 - Operational Noise Level - Statement of conforming emission level. 12 - Plant has no areas of excessive wear or damage. Mobile plant required to have; 1 - Plant is fitted with a Roll Over Protection Structure (R.O.P.S.) and operator restraint. 2 - Plant is fitted with a front horn and reversing beeper. 3 - Plant is fitted with a rotating or flashing amber beacon. Plant used to lift Material and equipment; Backhoes, excavators, cranes and loaders used as crane from designed lifting points. The Safe Working Load of the plant item is displayed on the plant as: EITHER; A Crane Chart supplied by the manufacturer specific to the plant item in the cabin of the plant for operator reference OR; The Safe Working Load of the equipment on the boom of the loader bucket and of the dipper arm of excavators - a combination of both is required for backhoes e.g. SWL 1.2ton. Personal Lifting Equipment - (Cherry Pickers, boom lift and elevated platform) 1 - Safety Working Load is displayed on work bucket / platform. 2 - Fully body harnesses and lanyards are to be provided for personnel using the equipment. 3 - Safety Instruction for the operation of the equipment is clearly displayed in the work bucket / platform. 4 - The supplier have provided training for personnel using the platform in the safe use of the equipment
Note on T24: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Do all personnel have the correct information, instruction and training according to their role and responsibilities? 2 - Is the contractor promoting awareness of company standards and regulations among their employees on a regular basis, or when it is necessary? 3 - Do all personnel have completed basic relevant awareness training, such as; Fire Awareness Training, Heat Stress awareness Training, Safety Signs and Color Code awareness Training, Environmental Awareness Training, Using Fire Extinguisher Awareness Training, Emergency reporting Awareness Training, Unsafe Act/Conditions reporting awareness training, Evacuation Procedure Awareness Training?
Note on C25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Crane Inspected 2 - Operator certified 3 - Lift Plan approved 4 - PTW obtained 5 - lifting equipment is suitable for the use it is being put to, marked with safe working load, properly maintained and inspected, and receives a periodic thorough examination. 6 - Are all members of the lifting operations team including the Appointed Person, Crane Drivers and Slingers / Signalers / Banksmen will be competent and have such practical and theoretical knowledge and experience as is necessary to carry out their duties. 7 - Bank man is available and certified 8 - The crane operator have a practical and theoretical knowledge of lifting operations 9 - Lifting operations will be undertaken by a minimum of three competent people the crane operator, slinger / signaler (slinger and signaler can be one person) / banks man / flagman (banks man and flagmen can be one person) and Supervisor 10 - Certification of Lifting Equipment / Lifting Gear / Lifting Devices 11 - Lifting plan prepared/approved/communicated 12 - Lifting gear (Chain sling, shackle, webbing sling, lifting clamps etc.) / devices (Chain block, Winch, Monorail etc.) are checked, inspected & tagged - ( size, length, dia, width, SWL,Condition & defects. 13 - All lifting equipment / gears have valid test certificates and are in good condition.
Note on T25: Refer MODON HSS Manual, Associated Procedures, Checklist and Standards: 1 - Is there process of SBO for leadership to identify and reinforce safe work practices/behaviors? 2 - Is there process of SBO for leadership to identify and improve on at-risk practices? 3 - Is there process of SBO for leadership to identify and improve on practices, conditions, controls, and compliance that eliminate or reduce hazards? 4 - Is there a process of SBO for leadership to make positive, corrective, cooperative, collaborative feedback/recommendations? 5 - Is there a training program for BBST, that how to identify critical safety behavior and how to provide feedback and the number of personnel trained. 6 - Is there a program for the leadership to carry out SBO once a month or twice (depends project scope of work), and record available?

## Major Quantities
MAJOR QUANTITIES
BOQ Number | Description of Item | Total Quantity | Unit of Measurement | Plan To Date | Actual To Date | Excecuted on site | Remaining Total | Variance
B1.32 11 13.01 | Subgrade | 20530 | m3 |  | 15000 | 15000 | 5530
B1.32 11 23.01 | Aggregate base course | 16375.94 | m3 |  | 9875.94 | 4625 | 6500
B4.33 31 23.01 | HDPE pipe | 5808 | m |  | 5808 |  | 0 | 0
B1.32 12 16.01 | Asphalt | 13360 | m3 |  | 573 | 573 | 12787
B1.32 14 13.13.01 | Interlock | 27900 | m2 |  | 0 |  | 27900
B1.32 16 13.23.01 | Curbstone | 20555 | m2 |  | 0 |  | 20555
B2.31 23 00.01 | Medium Voltage cables | 7120 | m |  | 0 |  | 7120
B2.33 71 00 02.01 | Low Voltage Cables, Copper & Aluminum, | 7500 | m |  | 7500 |  | 0
31 00 00 | Canopy | 4000 | m |  | 0 |  | 4000
03 00 00 | Platform | 4000 | m2 |  | 0 |  | 4000
B4.05 52 00.01 | Metal Handrail | 440 | m |  | 0 |  | 440
B2.26 56 19.01 | Lighting Luminaire | 116 | Unit |  | 0 |  | 116

## Invoice Log
Weekly Progress Report - Invoice Log | [32 empty] | Y
Project Value | [9 empty] | Payment Status | [7 empty] | Invoices Summary | [9 empty] | Average Invoices durations |  |  |  |  | N
Original Contract Value |  |  |  | 33090825 |  | O&M Value |  | 0 |  | Advance Payment % |  | 0% |  | Advance Payment (SAR) |  | 0 |  | No of Submitted Invoices |  | 2 |  | Submitted Invoices (SAR) |  | 3048399.33 |  | Submiited Invoice Peroid |  | CM / PgM Average Approval duration |  | 0 | Average Invoice Value | 0
Revised Contract Value |  |  |  | 0 |  | Revised O&M Value |  | 0 |  | Retention % |  | 0% |  | Retention (SAR) |  | 0 |  | No of Approved Invoices (CM) |  | 0 |  | Approved Invoices (CM) (SAR) |  | 0 |  |  |  | MODON PM & Accounts Average Approval duration |  | 0
Estimate At Completion Value |  |  |  | 33090825 |  | Submitted Invoices (Gross Value) |  | 3048399.33 |  | Penalties and deduction % |  | -0.006044% |  | AP Recovery (SAR) |  | 0 |  | No of Approved Invoices (PM) |  | 0 |  | Approved Invoices (PM) (SAR) |  | 0 |  | Invoice Submitted Compared to Contract Value | #DIV/0! | Payments Average Duration |  | 0
Potential Changes |  |  |  | 0 |  | Total Deduction |  | -2000 |  | Penalties and deduction (SAR) |  | -2000 |  | Retention Cumulative (SAR) |  | 0 |  | No of Paid Invoices |  | 0 |  | Paid Invoices (SAR) |  | 0 |  |  |  | Invoices Average total Duration
Invoice Reference |  |  |  | Invoice Value |  |  |  |  | Period Covered |  |  | CM / PgM Approval Timeline |  |  |  | Modon PM & Accounts Approval | [6 empty] | Payment Status |  |  |  |  | Total Invoice Duration | Remarks
# | Invoice No. | Doc Control reference | Submittal Rev. # | Gross Value | AP Recovery | Retention | VAT 5%/15% | Deduction / Penalties | Amount (net) | Start Date | End Date | Date to CM / PgM | CM / PgM Approval (Yes/No) | CM / PgM Reply Date | Days Elapsed | Date to PM | PM Approval (Yes/No) | PM Reply Date | Date to Accounts | Accounts Approval (Yes/No) | Accounts Approval Date | Days Elapsed | Date Paid | Amount Paid | Paid % | Payment Period (d) | Amount Pending
1 | 1 | SUD1-05-018-TDC-TS9-1-IPC-0001-00 | 0 | 2573925.6 | 0 |  | 386088.84 | -2000 | 2958014.44 | 2026-04-07 | 2026-07-18
9 | 2 | SUD1-05-018-TDC-TS9-1-IPC-0002-00 |  | 474473.73 |  |  | 71171.06 | 0 | 545644.79 | 2026-07-19 | 2026-08-30
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
|  |  | TOTAL | 3048399.33 | 0 | 0 |  | -2000 | 3503659.23 | [14 empty] | 0 |  |  | 0
Note on J3: Without O&M Cost

## Invoice Amount FIR
INVOICE AMOUNT FIR |  |  |  | 33090825
SL. | date of FIR | TOTAL AMOUNT | Total Amount % (as per FIR)
1 | 2026-07-22 | 2573925.6 | 7.778%
2 | 2026-08-30 | 474473.73 | 1.434%
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19

## FIR Summary
| Project Name |  | Construction of Passenger Station for SAR Railway Sudair Industrial City
| Project ID |  | SUD1-02-011 |  | Project Budget | 33090825
| Date Pariod |  | Start Date | 2026-04-07 | To | Data Date | 2026-10-19
SL NO | BOQ Item # | BOQ Description | Date | FIR # | FIR Description | Unit Rate | Current Pariod Quantity | % Claim | Unite rate as per claim | Total (SR)
|  | Description | [7 empty] | 3646338.729
1 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-15 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0014-01 | Check Coordinates level and Compaction F.D.T for Embankment 1st Layer for Station Road RD-01 , STA: 1+350 to STA: 1+700 | 24 | 5835.38 | 100% | 24 | 140049.12
2 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-11 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0015-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer for Station Road RD-01, STA: 0+850 to STA: 1+000 (Bottom subgrade) | 24 | 1733.54 | 100% | 24 | 41604.96
3 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-16 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0016-01 | Check Coordinates level and Compaction F.D.T for Embankment 1st Layer for Station Road RD-01 , STA: 0+120 to STA: 0+500 | 24 | 5229.11 | 100% | 24 | 125498.64
4 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-15 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0018-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st Layer for Station Road RD-01 , STA: 0+500 to STA: 1+000 | 24 | 6588.4 | 100% | 24 | 158121.6 | 8%
5 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-15 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0021-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer for Station Road RD-02, STA: 1+000 to STA:1+239.64 | 24 | 3557.97 | 100% | 24 | 85391.28
6 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-15 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0022-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer for Station Road RD-01, STA: 1+000 to STA:1+350 | 24 | 6159.64 | 100% | 24 | 147831.36
7 | B1.312323.01 | Earth works & Embankment | 2026-06-16 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0023-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer for Station Road RD-01, STA: 1+350 to STA:1+530 | 24 | 2536.83 | 100% | 24 | 60883.92
8 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-17 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0026-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer for Station Road RD-01, STA: 0+120 to STA:0+300 | 24 | 3205.93 | 100% | 24 | 76942.32
9 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-20 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0027-01 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer for Station Road RD-02, STA: 0+840 to STA:1+000 | 24 | 2713.88 | 100% | 24 | 65133.12
10 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-20 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0028-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer for Station Road RD-01, STA: 1+200 to STA:1+350 | 24 | 2471.63 | 100% | 24 | 59319.12
11 | B1.31 23.23.01 | Earth works & Embankment | 2026-06-21 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0029-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd Layer for Station Road RD-01, STA: 0+300 to STA:0+500 | 24 | 3412.82 | 100% | 24 | 81907.68
12 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-21 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0030-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd Layer for Station Road RD-01, STA: 0+500 to STA:0+700 | 24 | 3411.28 | 100% | 24 | 81870.72
13 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-21 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0031-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer for Station Road RD-01, STA: 1+000 to STA:1+200 | 24 | 3279.64 | 100% | 24 | 78711.36
14 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-21 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0032-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer for Station Road RD-02, STA: 0+600 to STA:0+700 | 24 | 1118.04 | 100% | 24 | 26832.96
15 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-23 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0033-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer for Station Road RD-02, STA: 0+860 to STA:1+000 | 24 | 1963.02 | 100% | 24 | 47112.48
16 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-22 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0034-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer for Station Road RD-01, STA: 0+700 to STA:0+850 | 24 | 2675.56 | 100% | 24 | 64213.44
17 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-22 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0035-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer for Station Road RD-01, STA: 0+850 to STA:1+000 | 24 | 2465.69 | 100% | 24 | 59176.56
18 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-22 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0036-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer for Station Road RD-02, STA: 1+000 to STA:1+239.64 | 24 | 3622.31 | 100% | 24 | 86935.44
19 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-23 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0037-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer for Station Road RD-01, STA: 0+120 to STA:0+300 | 24 | 3301.84 | 100% | 24 | 79244.16
20 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-23 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0038-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer for Station Road RD-02, STA: 0+550 to STA:0+700 | 24 | 2146.37 | 100% | 24 | 51512.88
21 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-24 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0039-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer for Station Road RD-01, STA: 0+300 to STA:0+500 | 24 | 3181.05 | 100% | 24 | 76345.2
22 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-24 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0040-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer for Station Road RD-01, STA: 0+850 to STA:1+000 | 24 | 2363.84 | 100% | 24 | 56732.16
23 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-25 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0041-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer for Station Road RD-01, STA: 0+120 to STA:0+300 | 24 | 3035.56 | 100% | 24 | 72853.44
24 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-25 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0042-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer for Station Road RD-01, STA: 1+200 to STA:1+350 | 24 | 1819.6 | 100% | 24 | 43670.4
25 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-27 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0043-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer for Station Road RD-01, STA: 1+380 to STA:1+530 | 24 | 1600.68 | 100% | 24 | 38416.32
26 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-20 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0044-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer for Station Road RD-02, STA: 0+570 to STA:0+600 | 24 | 422.84 | 100% | 24 | 10148.16
27 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-14 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0045-01 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer for Station Road RD-01, STA: 1+350 to STA:1+380 | 24 | 459.23 | 100% | 24 | 11021.52
28 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-27 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0046-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer for Station Road RD-01, STA: 1+000 to STA:1+200 | 24 | 3121.83 | 100% | 24 | 74923.92
29 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-28 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0047-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer for Station Road RD-01, STA: 0+300 to STA:0+500 | 24 | 2984 | 100% | 24 | 71616
30 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-28 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0048-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer for Station Road RD-01, STA: 1+530 to STA:1+700 (Bottom Subgrade) | 24 | 2264.12 | 100% | 24 | 54338.88
31 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-29 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0049-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer for Station Road RD-01, STA: 0+500 to STA:0+700 | 24 | 3745.61 | 100% | 24 | 89894.64
32 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-30 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0050-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer for Station Road RD-01, STA: 0+700 to STA:0+850 | 24 | 2120.15 | 100% | 24 | 50883.6
33 | B1 .31 23 23.01 | Earth works & Embankment | 2026-06-30 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0051-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer for Station Road RD-02, STA: 1+000 to STA:1+239.64 | 24 | 2901.29 | 100% | 24 | 69630.96
34 | B1.31 23 16.01 | Excavation (all types of soil) | 2026-09-08 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0052-02 | Check Coordinates level and Compaction F.D.T for Cutting Bottom Subgarde of road at Station Road RD-02, STA: 0+340 to STA:0+500 | 24 | 118.65 | 25% | 6 | 711.9
35 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-01 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0053-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer for Station Road RD-01, STA: 0+850 to STA: 1+000 | 24 | 2143.65 | 100% | 24 | 51447.6
36 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-04 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0055-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer for Station Road RD-01, STA: 1+000 to STA:1+200 | 24 | 2569.79 | 100% | 24 | 61674.96
37 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-04 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0056-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer for Station Road RD-01, STA: 1+200 to STA:1+350 | 24 | 1024.89 | 100% | 24 | 24597.36
38 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-22 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0057-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer for Station Road \ Carriage-way RD-02, STA: 0+730 to STA:0+840 (Bottom subgrade) | 24 | 234.51 | 100% | 24 | 5628.24
39 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-04 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0058-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer for Station Road RD-02, STA: 0+600 to STA:0+700 | 24 | 1290.07 | 100% | 24 | 30961.68
40 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-04 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0059-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer for Station Road RD-01, STA: 0+120 to STA: 0+300 (Bottom Subgrade) | 24 | 2301.88 | 100% | 24 | 55245.12
41 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-05 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0060-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer for Station Road RD-02, STA: 0+880 to STA:1+000 | 24 | 938.22 | 100% | 24 | 22517.28
42 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-06 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0061-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer for Station Road RD-01, STA: 0+300 to STA: 0+500 (Bottom Subgrade) | 24 | 2334.35 | 100% | 24 | 56024.4
43 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-06 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0062-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer for Station Road RD-01, STA: 0+500 to STA:0+700 (Bottom Subgrade) | 24 | 3250.21 | 100% | 24 | 78005.04
44 | B1 .31 23 16.01 | Earth works & Excavation / Cutting | 2026-07-06 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0063-00 | Check Coordinates level and Compaction F.D.T for Cutting Bottom Subgarde for Station Road RD-02, STA: 0+000 to STA:0+160 | 24 | 1335.84 | 100% | 24 | 32060.16
45 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-07 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0064-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer for Station Road RD-01, STA: 0+700 to STA:0+850 (Bottom Subgrade) | 24 | 2062.86 | 100% | 24 | 49508.64
46 | B1 .31 23 16.01 | Earth works & Excavation/cutting (all types of soil) | 2026-07-22 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0065-00 | Check Coordinates level and Compaction F.D.T for Cutting Bottom Subgrade for Station Road\ Carriage-way RD-02, STA: 0+730 to STA:0+840 | 24 | 515.37 | 25% | 6 | 3092.22
47 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-07 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0066-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer for Station Road RD-01, STA: 1+000 to STA: 1+200 (Bottom Subgrade) | 24 | 2348.09 | 100% | 24 | 56354.16
48 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-08 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0067-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer for Station Road RD-01, STA: 1+200 to STA: 1+350 (Bottom Subgrade) | 24 | 1209.65 | 100% | 24 | 29031.6
49 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-13 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0068-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer for Station Road RD-02, STA: 1+110 to STA:1+239.64 (Bottom sub grade) | 24 | 1033 | 100% | 24 | 24792
50 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-13 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0069-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer for Station Road RD-02, STA: 1+000 to STA:1+110 | 24 | 1219.05 | 100% | 24 | 29257.2
51 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-13 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0070-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer for Station Road RD-02, STA: 0+880 to STA:1+000 | 24 | 1443.25 | 100% | 24 | 34638
52 | B1 .31 23 16.01 | Earthwork & Excavation / Cutting | 2026-07-23 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0072-00 | Check Coordinates level and Compaction F.D.T for Cutting Bottom Subgrade for shoulders (left and right side) at Station Road RD-02, STA: 0+730 to STA:0+840 | 24 | 276.36 | 100% | 24 | 6632.64
53 | B1 .31 23 16.01 | Earth works & Embankment | 2026-07-23 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0073-00 | Check Coordinates and bottom level Road Filling and compaction test of bottom Sub-Grade of shoulders (left and right side) at Road # RD-02 STA: 0+730 to STA: 0+840 | 24 | 1024.52 | 100% | 24 | 24588.48
54 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-27 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0074-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer for Station Road RD-02, STA: 1+030 to STA:1+110 (Bottom Sub grade) | 24 | 739.52 | 100% | 24 | 17748.48
55 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-28 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0075-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer (Road and shoulders) for Station Road RD-02, STA: 0+880 to STA:1+030 | 24 | 1687.63 | 100% | 24 | 40503.12
56 | B1 .31 23 16.01 | Earth works & Embankment | 2026-07-29 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0076-00 | Check Coordinates level and Compaction F.D.T for Cutting Bottom Subgrade of road at Station Road RD-02, STA: 0+160 to STA:0+340 | 24 | 183.94 | 100% | 24 | 4414.56
57 | B1 .31 23 23.01 | Earth works & Embankment | 2026-07-29 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0077-00 | Check Coordinates and bottom level Road Filling and compaction test of bottom Sub-Grade of Road/Carriageway at Road # RD-02 STA: 0+160 to STA: 0+340 | 24 | 420.3 | 100% | 24 | 10087.2
58 | B1 .31 23 16.01 | Earth works & Embankment | 2026-07-29 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0078-00 | Check Coordinates level and Compaction F.D.T for Cutting Bottom Subgrade of road at Station Road RD-01, STA: 1+850 to STA:1+914.20 | 24 | 327.47 | 100% | 24 | 7859.28
59 | B1 .31 23 23.01 | Earth works & Embankment | 2026-08-01 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0080-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer for Station Road RD-02, STA: 0+840 to STA:0+880 | 24 | 475.3 | 100% | 24 | 11407.2
60 | B1 .31 23 23.01 | Earth works & Embankment | 2026-08-05 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0081-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer for Station Road RD-02, STA: 0+600 to STA:0+700 | 24 | 1191.58 | 100% | 24 | 28597.92
61 | B1 .31 23 23.01 | Earth works & Embankment | 2026-08-05 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0083-00 | Check Coordinates level and Compaction F.D.T for Embankment Bottom Subgrade layer for Station Road RD-01, STA: 1+700 to STA:1+850 | 24 | 3527.28 | 100% | 24 | 84654.72
62 | B1 .31 23 23.01 | Earth works & Embankment | 2026-08-05 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0084-00 | Check Coordinates level and Compaction F.D.T for Embankment3rd layer for Station Road RD-02, STA: 0+510 to STA:0+600 | 24 | 1181.28 | 100% | 24 | 28350.72
63 | B1 .31 23 23.01 | Earth works & Embankment | 2026-08-10 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0090-00 | Check Coordinates level and Compaction F.D.T for Embankment 6th layer (Road and shoulders) for Station Road RD-02, STA: 0+840 to STA:1+030 (Bottom Sub grade) | 24 | 1632.57 | 100% | 24 | 39181.68
64 | B1 .31 23 23.01 | Earth works & Embankment | 2026-08-15 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0096-00 | Check Coordinates level and Compaction F.D.T for Embankment Bottom Subgrade layer for Station Road RD-02, STA: 0+500 to STA:0+730 | 24 | 2707.85 | 100% | 24 | 64988.4
65 | B1 .31 23 23.01 | Earth works & Embankment/Fill | 2026-10-03 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0099-02 | Check Coordinates and bottom level Road Filling and compaction test of bottom Sub-Grade of Road/Carriageway at Road # RD-02 STA: 0+340 to STA: 0+500 | 18 | 761.53 | 10% | 1.8 | 1370.754
66 | B1 33 71 00 02 01 | Road Crossing Duct for Street Lighting cables UPVC (2xØ110mm) | 2026-08-22 | SUD1-05-018-TDC-TS9-1-LIT-FIR-0100-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X110mm) from Manhole 05 To Manhole 06 for Street Lighting Duct Bank in Roundabout Road RD-01 & RD-02 | 1617 | 57.9 | 25% | 404.25 | 23406.075
67 | B1 33 71 00 02 01 | Road Crossing Duct for Street Lighting cables UPVC (2xØ110mm) | 2026-08-22 | SUD1-05-018-TDC-TS9-1-LIT-FIR-0101-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X110mm) from Manhole 03 To Manhole 04 for Street Lighting Duct Bank in Road RD-02 | 1617 | 13 | 25% | 404.25 | 5255.25
68 | B1 33 71 00 02 01 | Road Crossing Duct for Street Lighting cables UPVC (2xØ110mm) | 2026-08-22 | SUD1-05-018-TDC-TS9-1-LIT-FIR-0102-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X110mm) from Manhole 07 To Manhole 08 for Street Lighting Duct Bank in Road RD-02 | 1617 | 13 | 25% | 404.25 | 5255.25
69 | B2.33 71 00 02.02 | Road Crossing Duct for Street Lighting cables UPVC (4xØ110mm) | 2026-08-23 | SUD1-05-018-TDC-TS9-1-LIT-FIR-0105-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (4X110mm) from Manhole 01 To Manhole 02 for Street Lighting Duct Bank in Road RD-01 | 525 | 9.05 | 25% | 131.25 | 1187.8125
70 | B2.33 71 00 02.02 | Road Crossing Duct for Street Lighting cables UPVC (4xØ110mm) | 2026-08-23 | SUD1-05-018-TDC-TS9-1-LIT-FIR-0106-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (4X110mm) from Manhole 09 To Manhole 10 for Street Lighting Duct Bank in Road RD-02 | 525 | 9.05 | 25% | 131.25 | 1187.8125
71 | B2.33 71 00 02.01 | Road Crossing Duct for Street Lighting cables UPVC (4xØ110mm) | 2026-08-23 | SUD1-05-018-TDC-TS9-1-LIT-FIR-0107-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for UPVC Pipe (2X110mm) from Manhole 11 To Manhole 12 for Street Lighting Duct Bank in Road RD-02 | 327 | 15.9 | 45% | 147.15 | 2339.685
72 | B2.1.33 81 26.06 | Road crossing ducts, (6*50mm) HDPE | 2026-08-23 | SUD1-05-018-TDC-TS9-1-TEL-FIR-0108-00 | Check levels, Laying polyethylene sheet, Form work and concrete pouring for TELECOMMUNICATIONS Works Duct Bank for HDPE Pipe 3(2X50mm) From Manhole 05 To 06 in Road RD-02 | 124 | 40.61 | 25% | 31 | 1258.91
73 | B3.33 14 13.01 | Potable Water Network: 75mm Diameter (Depth: 0.0m - 1.5m) | 2026-08-31 | SUD1-05-018-TDC-TS9-1-PW-FIR-0109-00 | Check Coordinates level and Excavation width Bottom level and compaction for potable water pipeline from Station ST: 0+250 to ST: 1+900 #RD-02 | 106 | 1650 | 5% | 5.3 | 8745
74 | B4.33 31 23.01 | Sewarage Network: HDPE force main110 mm diameter (Depth: 0- 1.5m) | 2026-08-27 | SUD1-05-018-TDC-TS9-1-SEW-FIR-0110-00 | Check Coordinates level and Excavation width Bottom level and compaction for Sewerage pipeline trench from Station ST: 1+060 to ST: 2+625 #RD-01 | 143 | 1565 | 10% | 14.3 | 22379.5
75 | B5.33.42.13.01 | Storm Water Network: Concrete pipe culverts (900mm) Diameter | 2026-09-06 | SUD1-05-018-TDC-TS9-1-STR-FIR-0111-00 | Check Coordinates level and Excavation width Bottom level and compaction for Precast concrete pipe culvert (900mm) diameter at #RD-01 | 1018 | 195 | 10% | 101.8 | 19851
76 | B1.31 23 23.01 | Earth works & Embankment/Fill | 2026-09-14 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0114-00 | Check Coordinates and bottom level Road Filling and compaction test of Median Island 1st layer at Road # RD-01 STA: 1+500 to STA: 1+850 | 24 | 285.6 | 10% | 2.4 | 685.44
77 | B1.31 23 23.01 | Earth works & Embankment | 2026-09-14 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0115-00 | Check Coordinates level and Compaction F.D.T for Embankment 1st layer from St:0+000 to 0+062.93 Parking Station Road | 24 | 4750.08 | 100% | 24 | 114001.92
78 | B1.31 23 23.01 | Earth works & Embankment | 2026-09-19 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0116-00 | Check Coordinates level and Compaction F.D.T for Embankment 2nd layer from St:0+000 to 0+062.93 Parking Station Road | 24 | 1105.46 | 100% | 24 | 26531.04
79 | B5.33 42 13.01 | Storm Water Network: Concrete pipe culverts (900mm) Diameter | 2026-09-24 | SUD1-05-018-TDC-TS9-1-STR-FIR-0117-00 | Check Pipe installation of Precast concrete pipe culvert (900mm) diameter at #RD-01 | 1018 | 195 | 30% | 305.4 | 59553
80 | B1 31 23 23 01 | Check Installation Manhole MH-18 for TELECOMMUNICATIONS Works in Road COL-MC10 | 2026-09-29 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0123-00 | Check Coordinates level and Compaction F.D.T for Embankment 3rd layer from St:0+000 to 0+062.93 Parking Station Road | 5939 | 1185.51 | 0% | 0 | 0
81 | B2.1.33 81 26.04 | Earth works & Embankment | 2026-10-07 | SUD1-05-018-TDC-TS9-1-TEL-FIR-0124-01 | Check Installation Manhole MH-18 for TELECOMMUNICATIONS Works in Road COL-MC10 | 24 | 1 | 100% | 24 | 24
82 | B2.1.33 81 26.03 | Check Installation Manhole MH-11 & MH-12 & MH-15 & MH-16 & MH-17 for TELECOMMUNICATIONS Works in Road COL-MC10 & RD-01 | 2026-09-30 | SUD1-05-018-TDC-TS9-1-TEL-FIR-0125-00 | Check Installation Manhole MH-11 & MH-12 & MH-15 & MH-16 & MH-17 for TELECOMMUNICATIONS Works in Road COL-MC10 & RD-01 | 5811 | 5 | 30% | 1743.3 | 8716.5
83 | B1 32 11 13 01 | Subgrade | 2026-09-30 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0127-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road /Carriageway # RD-01 STA: 0+150 to STA: 0+650(Left side) | 36 | 1312.5 | 10% | 3.6 | 4725
84 | B2.26 05 19.01 | 4Cx 6mm2 + 1Cx6mm2 Cu/XLPE/SWA/PVC | 2026-09-30 | SUD1-05-018-TDC-TS9-1-LIT-FIR-0128-00 | Check Sand Bedding and Laying of U/G LV Cables (4Cx6+6E) for Bollard Lighting Network in landscape Area near Modon Office | 24 | 2200 | 45% | 10.8 | 23760
85 | B5.33 42 13.05 | Storm Water Network: Concrete pipe culverts | 2026-10-04 | SUD1-05-018-TDC-TS9-1-STR-FIR-0131-00 | Check Steel Reinforcement and concrete pouring for Base slab | 29950 | 2 | 25% | 7487.5 | 14975
86 | B1.31 23 23.01 | Earth works & Embankment | 2026-10-05 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0134-00 | Check Coordinates level and Compaction F.D.T for Embankment 4th layer from St:0+000 to 0+062.93 Parking Station Road | 24 | 1236.3 | 100% | 24 | 29671.2
87 | B1.32 11 13.01 | Subgrade | 2026-10-06 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0135-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road /Carriageway # RD-01 STA: 0+650 to STA: 0+900 (left side) | 36 | 656.25 | 10% | 3.6 | 2362.5
88 | B1.32 11 13.01 | Subgrade | 2026-10-06 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0137-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road /Carriageway # RD-01 STA: 0+900 to STA: 1+200 (left side) | 36 | 787.5 | 10% | 3.6 | 2835
89 | B2.1.33 81 26.03 | Manhole Type 1 | 2026-10-07 | SUD1-05-018-TDC-TS9-1-TEL-FIR-0138-00 | Check Installation Manhole MH-03 & MH-04 & MH-07 & MH-08 & MH-09 & MH-10 for TELECOMMUNICATIONS Works in Road RD-01& RD-02 | 5811 | 6 | 25% | 1452.75 | 8716.5
90 | B2.1.33 81 26.04 | Manhole Type 2 | 2026-10-08 | SUD1-05-018-TDC-TS9-1-TEL-FIR-0139-00 | Check Installation Manhole MH-02 & MH-05 & MH-06 & MH-14 for TELECOMMUNICATIONS Works in Road COL-MC10 & RD-02 | 5939 | 4 | 25% | 1484.75 | 5939
91 | B1.32 11 13.01 | Subgrade | 2026-10-10 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0140-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road /Carriageway # RD-01 STA: 1+200 to STA: 1+500 (Left side) | 36 | 787.5 | 10% | 3.6 | 2835
92 | B1.32 11 13.01 | Subgrade | 2026-10-10 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0141-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road /Carriageway # RD-01 STA: 1+500 to STA: 1+850 (Left side) | 36 | 918.75 | 10% | 3.6 | 3307.5
93 | B1.32 11 23.01 | Aggregate Base Courses | 2026-10-11 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0142-01 | Check Coordinates level and compaction F.D.T for (Aggregate base course) at Road /Carriageway# RD-01 STA: 0+170 to STA: 0+650(Left Side) | 66 | 840 | 10% | 6.6 | 5544
94 | B1.31 23 23.01 | Earth works & Embankment | 2026-10-12 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0143-00 | Check Coordinates level and Compaction F.D.T for Embankment 5th layer from St:0+000 to 0+062.93 Parking Station Road | 24 | 1515.03 | 100% | 24 | 36360.72
95 | B5.33 42 13.01 | Storm Water Network: Concrete pipe culverts (900mm) Diameter | 2026-10-14 | SUD1-05-018-TDC-TS9-1-STR-FIR-0144-00 | Check Concrete pouring on top of Precast concrete pipe culvert (900mm) diameter at #RD-01 | 1018 | 195 | 25% | 254.5 | 49627.5
96 | B5.33 42 13.05 | Storm Water Network: Concrete pipe culverts | 2026-10-14 | SUD1-05-018-TDC-TS9-1-STR-FIR-0145-00 | Check Steel Reinforcement and concrete pouring for wing walls, and headwall of Outlet and inlet structures | 29950 | 2 | 25% | 7487.5 | 14975
97 | B1.32 11 23.01 | Aggregate Base Courses | 2026-10-14 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0148-00 | Check Coordinates level and compaction F.D.T for (Aggregate base course) at Road /Carriageway# RD-01 STA: 0+650 to STA: 1+200(Left Side) | 66 | 962.5 | 10% | 6.6 | 6352.5
98 | B1.32 11 13.01 | Subgrade | 2026-10-14 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0149-00 | Check Coordinates level and Compaction F.D.T for (Subgrade) 2nd layer at Road /Carriageway # RD-01 STA: 0+160 to STA: 0+650 (Right side) | 36 | 1312.5 | 10% | 3.6 | 4725
99 | B3.33 14 13.01 | Potable Water Network: 75mm Diameter (Depth: 0.0m - 1.5m) | 2026-10-17 | SUD1-05-018-TDC-TS9-1-PW-FIR-0150-00 | Check Coordinates level and Excavation width Bottom level and compaction for potable water pipeline from Station ST: 2+350 to ST: 2+725 #RD-02 | 106 | 375 | 5% | 5.3 | 1987.5
100 | B1.32 11 26.01 | BITUMINOUS BASE COURSE | 2026-10-17 | SUD1-05-018-TDC-TS9-1-ROD-FIR-0151-00 | Check Coordinates, level, thickness, Compaction and Testing for Bituminous base course 1st layer (80mm) on Road /Carriageway from STA:0+170 to STA: 0+550 at Road #RD-01 | 533 | 266 | 10% | 53.3 | 14177.8
3887955.949

## CCO
CONTRACT CHANGE ORDER (CCO)
CCO No. | Date Added | Description of Change | Status | SR | Sch Impact (Months) | Date Approved | Duration (days)
- | - | - | - | - | - | - | -

## Procurement
PROCUREMENT
Sr. NO. | Project ID | ACT#inP6 | Item Description | Discipline | (Long \Short) Lead Items | BOQ. No. | Unit | Quantity | Proc. Qty | Required P.O Date | Date of Pur. Order Issued | Purchase Order No. | Supplier | Supplier Phone | Method of Shipping | Required on Job | E.D.A. to Site | A.D.A. to Site | Lead Time | Approval Status | The Impact (BOQ Cost) | Completion Rate | Remarks
1 | SUD1-05-018 | SDR-ST-PRO-S-1010 | Waterproofing (Thermal & moisture Protection) | Civil | Short Lead Items | 07 00 00 | m2 | 910 | 910 | 2026-08-10 | - | - | - |  | Local trancport | Civil | 2026-09-04 | 2026-11-04 | 25 | Approved | - | -
2 | SUD1-05-018 | SDR-ST-PRO-S-1030 | Interlock | Civil | Short Lead Items | 33 42 16 | m2 | 27900 | 27900 | 2026-09-02 | - | - | - |  | Local trancport | Civil | 2026-09-28 | 2026-11-19 | 26 | Approved | - | - | on going
3 | SUD1-05-018 | SDR-ST-PRO-S-1060 | Kerbstone | Civil | Short Lead Items | 32 11 26 | m | 20555 | 20555 | 2026-09-03 | - | - | - |  | Local trancport | Civil | 2026-09-17 | 2026-11-17 | 14 | Approved | - | - | on going
4 | SUD1-05-018 | SDR-ST-PRO-S-1260 | Steel Bars | Civil | Short Lead Items | 05 12 00 | Unit | 1 | 1 | 2026-06-01 | - | - | - |  | Local trancport | Civil | 2026-07-22 | 2026-09-20 | 51 | Approved | - | 90% | on going
5 | SUD1-05-018 | SDR-ST-PRO-S-1270 | Asphalt | Civil | Short Lead Items | 32 12 16 | m3 | 3420 | 3420 | 2026-10-27 | - | - | - |  | Local trancport | Civil | 2026-11-10 | 2027-02-09 | 14 | Approved | - | 4.3% | on going
6 | SUD1-05-018 | SDR-ST-PRO-S-1140 | LOW VOLTAGE CABLES | Electrical | Short Lead Items | 33 71 00 02 | m | 695 | 695 | 2026-08-31 | 2026-06-18 | PO 12507 | - |  | Local trancport | Civil | 2026-09-11 | 2026-10-11 | 11 | Approved | - | 100% | Delivered
7 | SUD1-05-018 | SDR-ST-PRO-S-1150 | LOW VOLTAGE DISTRIBUTION Panel | Electrical | Short Lead Items | 33 71 26 | Unit | 1 | 1 | 2026-08-28 | - | - | - |  | Local trancport | Civil | 2026-09-18 | 2026-11-18 | 32 | Approved | - | - | on going
8 | SUD1-05-018 | SDR-ST-PRO-S-1160 | STREET LIGHTING FEEDER Panel | Electrical | Short Lead Items | 33 71 26 03 | Unit | 2 | 2 | 2026-09-07 | - | - | - |  | Local trancport | Civil | 2026-09-21 | 2026-11-01 | 14 | Approved | - | - | on going
9 | SUD1-05-018 | SDR-ST-PRO-S-1170 | STREET LIGHTING CABLES | Electrical | Short Lead Items | 33 71 00 01 | Unit | 6800 | 6800 | 2026-08-31 | - | - | - |  | Local trancport | Civil | 2026-09-14 | 2026-11-14 | 14 | Approved | - | 100% | Delivered
10 | SUD1-05-018 | SDR-ST-PRO-S-1200 | ROAD CROSSING DUCTS Ø110mm | Electrical | Short Lead Items | 33 81 26 | Unit | 104 | 104 | 2026-08-18 | - | - | - |  | Local trancport | Civil | 2026-09-28 | 2026-11-02 | 19 | Approved | - | 100% | Delivered
12 | SUD1-05-018 | SDR-ST-PRO-S-1230 | CCTV :5MP IP PoE Bullet Camera | Electrical | Short Lead Items | B2.28.20.00.01 | unit | 16 | 16 | 2026-09-01 | - | - | - |  | Local trancport | Electrical | 2026-09-17 | 2026-10-28 | 16 | Approved | - | - | on going
13 | SUD1-05-018 | SDR-ST-PRO-S-1240 | CCTV :Pole mounted Filed Equipment cabinet (FE | Electrical | Short Lead Items | B2.28.20.00.02 | unit | 4 | 4 | 2026-10-26 | - | - | - |  | Local trancport | Electrical | 2026-11-06 | 2027-01-05 | 11 | Approved | - | - | on going
14 | SUD1-05-018 | SDR-ST-PRO-S-1250 | VOICE EVACUATION SYSTEM | Electrical | Short Lead Items | 27 40 00 | Unit | 32 | 32 | 2026-10-29 | - | - | - |  | Local trancport | Electrical | 2026-11-11 | 2027-01-10 | 13 | Approved | - | - | on going
15 | SUD1-05-018 | SDR-ST-PRO-S-1040 | HDPE PIPES & FITTINGS | Mechanical | Short Lead Items | 33 31 23 | m | 2946 | 2946 | 2026-08-24 | 2026-06-15 | PO 12272 |  |  | Local trancport | Electrical | 2026-09-18 | 2026-11-18 | 25 | Approved | - | 100% | Delivered
16 | SUD1-05-018 | SDR-ST-PRO-S-1050 | CONCRETE PIPES AND FITTINGS | Mechanical | Short Lead Items | 33 42 13 | m | 230 | 230 | 2026-09-07 |  |  |  |  | Local trancport | Electrical | 2026-09-18 | 2026-12-07 | 11 | Approved | - | 100% | Delivered
19 | SUD1-05-018 | SDR-ST-PRO-S-1090 | MANHOLE, CATCH BASIN & VALVE BOX COVER | Mechanical | Short Lead Items | 33 81 26 | Unit | 16 | 16 | 2026-09-14 | - |  |  |  | Local trancport | Electrical | 2026-09-28 | 2026-12-07 | 14 | Approved | - | -
20 | SUD1-05-018 | SDR-ST-PRO-S-1000 | Metal railing for platform | Civil | Long Lead Items | 05 52 00 | m | 440 | 440 | 2026-08-25 | - |  |  |  | Local trancport | Electrical | 2026-10-28 | 2027-02-02 | 64 | Not submitted | - | -
21 | SUD1-05-018 | SDR-ST-PRO-S-1020 | Canopy | Civil | Long Lead Items | 03 30 00/03 53 00 | 560 | m2 | m2 | 2026-11-19 | - |  |  |  | Local trancport | Mechanical | 2026-12-22 | 2027-04-08 | 33 | Not submitted | - | -
22 | SUD1-05-018 | SDR-ST-PRO-S-1110 | MEDIUM VOLTAGE CABLES DUCT BANKS | Electrical | Long Lead Items | 33 71 00 | m | 105 | 105 | 2026-10-12 | - |  |  |  | Local trancport | Mechanical | 2026-10-29 | 2027-02-14 | 17 | Not submitted | - | -
23 | SUD1-05-018 | SDR-ST-PRO-S-1120 | MEDIUM VOLTAGE CABLES | Electrical | Long Lead Items | 33 71 49.23 | Unit | 7120 | 7120 | 2026-10-12 | - |  |  |  | Local trancport | Mechanical | 2026-10-30 | 2027-02-15 | 18 | Not submitted | - | -
24 | SUD1-05-018 | SDR-ST-PRO-S-1130 | SUB-STATION | Electrical | Long Lead Items | 33 73 00 | unit | 2 | 2 | 2026-10-19 | - |  |  |  | Local trancport | Mechanical | 2026-12-03 | 2027-03-04 | 45 | Not submitted | - | -
25 | SUD1-05-018 | SDR-ST-PRO-S-1180 | LIGHTING POLES | Electrical | Long Lead Items | 33 71 16 | m | 143 | 143 | 2026-10-19 | 2026-07-01 | PO 12725 | - |  | Local trancport | Mechanical | 2026-11-05 | 2027-02-27 | 17 | Not submitted | - | -
26 | SUD1-05-018 | SDR-ST-PRO-S-1190 | STREET LIGHTING LUMINAIRE | Electrical | Long Lead Items | 26 56 19 | Unit | 276 | 276 | 2026-11-10 | - |  | - |  | Local trancport | Civil | 2026-12-18 | 2027-03-25 | 38 | Not submitted | - | -
27 | SUD1-05-018 | SDR-ST-PRO-S-1220 | Outdoor Lighting Fixtures | Electrical | Long Lead Items | 26 56 00 | Unit | 390 | 390 | 2026-11-23 | - |  | - |  | Local trancport | Civil | 2026-12-10 | 2027-04-11 | 17 | Not submitted | - | -
28 | SUD1-05-018 | SDR-ST-PRO-S-1100 | WASHOUT & AIR VALVE, GATE VALVE, BUTTERFLY VALVE | Mechanical | Long Lead Items | 33 14 19 | Unit | 5 | 5 | 2026-10-26 | - |  | - |  | Local trancport | Electrical | 2026-12-08 | 2027-03-25 | 43 | Approved | - | - | on going
[22 empty] | 15% | Under delivery
100%
#REF!
Y

## Manpower
Head-Count ( Non Manual)
MONTHS | 2026-04-07 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31
Plan - Monthly | 12 | 16 | 20 | 29 | 30 | 30 | 32 | 32 | 32 | 30 | 28 | 24 | 21 | 20 | 19 | 21 | 15
Planned - Cumulative | 12 | 24 | 40 | 60 | 89 | 119 | 149 | 181 | 213 | 245 | 275 | 303 | 327 | 348 | 368 | 387 | 408
Actual - Monthly | 12 | 16 | 16 | 16 | 22 | 16 | 22
Actual Cumulative | 12 | 28 | 44 | 60 | 82 | 98 | 120
Forecast - Monthly
Saudi Monthly - Actual
Head-Count (Manual)
MONTHS | 2026-04-07 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31
Plan - Monthly | 18 | 30 | 36 | 41 | 47 | 123 | 185 | 200 | 230.9885 | 226.4271 | 218.5613 | 203.8346 | 202.603 | 135.9892 | 137.2848 | 105.6091 | 6.7546
Planned - Cumulative | 18 | 48 | 84 | 125 | 172 | 295 | 480 | 680 | 910.9885 | 1137.4156 | 1355.9769 | 1559.8115 | 1762.4145 | 1898.4037 | 2035.6885 | 2141.2976 | 2148.0522
Actual - Monthly | 41 | 48 | 62 | 65 | 31 | 31 | 65 | [21 empty] | 0
Actual Cumulative | 41 | 89 | 151 | 216 | 247 | 278 | 343
Forecast - Monthly
Saudi - Actual
Head-Count (Non-Manual) | [24 empty] | Month |  | 2026-10-31 | 2026-11-30
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff
20 | 22 |  | 2 |  | 0 |  | 3
Head-Count (Manual) | [10 empty] | Man Power by Trade
Planned | Actual |  | Variance |  | Forecast Next Month |  | Saudi Staff |  |  |  | Key Trade |  | Engineer |  | Doc. Controller |  | Proc. Team | Foreman | Draftman | Driver | UnSkilled Labor | Skiled labour | Others | Total
40 | 65 |  | 25 |  | 0 |  | 0 |  |  |  | Plan |  | 2 |  | 1 |  | 1 | 2 | 1 | 5 | 15 | 8 | 5 | 40
[11 empty] | Actual |  | 10 |  | 1 |  | 1 | 3 | 1 | 31 | 20 | 10 | 10 | 87
Equipment
MONTHS | 2026-04-07 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31
Plan - Monthly | 0 | 6.3077 | 6.2422 | 22.2758 | 28.8469 | 47.771 | 56.6443 | 61.6303 | 46.2149 | 31.3329 | 14.952 | 13.8573 | 10.0747 | 8.9238 | 8 | 0 | 0
Planned - Cumulative | 0 | 6.3077 | 12.6154 | 18.8575 | 41.1333 | 69.9803 | 117.7513 | 174.3956 | 236.0259 | 282.2408 | 313.5737 | 328.5257 | 342.383 | 352.4577 | 361.3815 | 369.3815 | 369.3815
Actual - Monthly | 0 | 6 | 14 | 17 | 32 | 18 | 32
Actual Cumulative | 0 | 6 | 20 | 37 | 69 | 87 | 119
Forecast - Monthly
Equipment Count
Planned | Actual |  | Idle |  | Variance |  | Forecast Next Month
28.8469 | 32 | 56.6443 | 0 |  | 3.1531 |  | 0
Type | Pick Up/Car | Fork lift | Bus | Dumper | Dump Truck | Grader | Boom Truck |  | Generator |  | CRANE |  | Showel |  | Grader |  | Truck | Water Tank | Finisher | Bobcat | Forklift | JCB | Loader | Boom Truck | Road Marker | Total
Plan | 1 |  | 1 |  | 10 |  | 0 |  | 1 |  | 0 |  | 0 |  | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 22
Actual | 2 |  | 1 |  | 10 |  | 0 |  | 1 |  | 1 |  | 1 |  | 5 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23
Idle | [25 empty] | 0

## Issues
[12 empty] | 2026-10-19 | Status | Responsibility
[13 empty] | Open | Contractor
[13 empty] | Closed | Consultant
Modon
Third Party
Other
Issue Log
Issue ID | Parent Project ID | Contract / Project ID | Project Name | City | Region | Fund Source | Phase | PM / Owner | Contractor / Designer | Current Status | Value (SAR) | Category | Issue Title | Description | Evidence / Data | Severity (1-5) | Urgency (1-5) | Priority Score | Priority | Action Required | Date Raised | Status | Duration Elapsed | Expected/Actual Closure | Target Date
3120-1 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Access & Permits | Egis / MODON | Technical Development Company for Contracting | Close |  |  |  | Noticed a signboard that is fallen and improperly positioned on the ground |  |  |  |  | Contractor | Assess the damage: Evaluate whether the sign can be repaired and reinstalled, or if it needs a complete replacement.Inspect the mounting hardware: Determine why it fell. Check for rusted bolts, rotted wood, cracked concrete bases, or loose brackets.Reinstall securely: Remount the sign using upgraded, weather-resistant hardware (such as heavy-duty anchor bolts or reinforced brackets) that can withstand local wind loads and environmental conditions. | 2026-09-02 | Closed | 1 | 2 | 2026-09-02
3120-2 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Design / Engineering | Egis / MODON | Technical Development Company for Contracting | Close |  |  |  | Waste plastic bottles were scattered on-site, resulting in poor housekeeping. |  |  |  |  | Contractor | Informed the workgroup about the concern to clean up the area immediately, set up proper disposal bins, and run a short safety reminder for the crew. | 2026-09-04 | Closed | 1 | 2 | 2026-09-04
3120-3 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  |  |  | A new water filter was installed to ensure clean drinking water. |  |  |  |  | Contractor | GOOD PRACTICE | 2026-09-06 | Closed | 1 | 2 | 2026-09-06
3120-4 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  |  |  | It was observed that the subcontractor was carrying out pipe-shifting activities using a wheel loader. |  |  |  |  | Contractor | Stop Work: Issue an immediate Stop Work Order to halt the pipe-shifting activity safely.Secure the Area: Ensure the load is safely lowered to the ground and the area is barricaded if necessary.Conduct a Safety Stand-Down: Brief the supervisor and workers involved on the specific hazards of using unauthorized machinery for lifting. Review Risk Assessment & Method Statement (RAMS): Verify if the approved RAMS specified a wheel loader. If not, enforce compliance; if it did, revise the RAMS immediately to reflect proper lifting equipment.Verify Operator Competency: Check the operator's license and verify if they have undergone specific training for material handling.Enforce Proper Equipment: Mandate the use of appropriate lifting equipment, such as a crane, boom truck, or an excavator fitted with an approved lifting hook and certified slings/shackles | 2026-09-08 | Closed | 1 | 2 | 2026-09-08
3120-5 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  |  |  | Concrete barriers were misplaced in the area |  |  |  |  | Contractor/HSE Team | Use appropriate heavy lifting equipment (such as a Boomtruck) to move the concrete barriers back to a safe distance—away from the excavation edge. | 2026-09-09 | Closed | 1 | 2 | 2026-09-09
3120-6 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  |  |  | Dust created by vehicles moving on project routes |  |  |  |  | Contractor | Water spraying on vehiceles routes on regular basis | 2026-09-20 | Closed | 1 | 2 | 2026-09-20
3120-7 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  |  |  | Unaviailibilty of shaded cold water station |  |  |  |  | Contractor/HSE Team | Provision of shaded cold water station to the site workers. | 2026-09-20 | Closed | 1 | 2 | 2026-09-20
3120-8 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  |  |  | Shallow excavation found without safety and warning signages |  |  |  |  | Contractor/HSE Team | posting warning and safety signages to increase the visibility and awareness about riks. | 2026-09-24 | Closed | 1 | 2 | 2026-09-24
3120-9 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  |  |  | Workers found in equipment working zone |  |  |  |  | Contractor/HSE Team | Stop movement in man machine/ equioment interface and segrete equipment and man working areas. | 2026-09-24 | Closed | 1 | 2 | 2026-09-24
3120-10 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  |  |  | Directional signages along with concrete jersey barriers and warning signages and tape were found missing | Contractor HSE team | Directional signages along with concrete jersey barriers and warning tape with rope have been provided – New Diversion Road,to ensure safe traffic movement and to guide site vehicles / heavy equipment. |  |  | Contractor HSE team | Directional signages along with concrete jersey barriers and warning tape with rope have been provided – New Diversion Road,to ensure safe traffic movement and to guide site vehicles / heavy equipment. | 2026-10-03 | Closed | 1 | 2 | 2026-10-03
3120-11 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  |  |  | Equipment operator found working zone with Non-compalince to site mandatory PPE. | Contractor consruction /HSE Team | it was ensure to wear the mandatory PPE all the time when present on site |  |  | Contractor consruction /HSE Team | it was ensure to wear the mandatory PPE all the time when present on site | 2026-10-03 | Closed | 1 | 2 | 2026-10-03
3120-12 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  |  |  | Observe Hot Work activity without proper control measure Fire safety |  |  |  |  | Contractor HSE team | Provide Fire Extinguisher and other requirements as per Hot work requirements. | 2026-10-10 | Closed | 1 | 2 | 2026-10-10
3120-13 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  |  |  | Observe site without mandatory PPE complaince |  |  |  |  | Contractor consruction /HSE Team | Wear the mandatory PPE all the time when present on site | 2026-10-11 | Closed | 1 | 2 | 2026-10-11
3120-14 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  |  |  | Observe dust created at temporary vehicles roads due insuffient dust control measures. |  |  |  |  | Contractor HSE team | Ensure dust control by regular spraying of water on vehicles routes | 2026-10-18 | Closed | 1 | 2 | 2026-10-18
3120-15 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  |  |  | Observe non complaince of mandatory PPE by equipment operators |  |  |  |  | Contractor consruction /HSE Team | Wear the mandatory PPE all the time by equipment operators when present on site | 2026-10-17 | Closed | 1 | 2 | 2026-10-17

## Risk Register
Risk Log
Risk ID | Parent Project ID | Contract / Project ID | Project Name | City | Region | Fund Source | Phase | PM / Owner | Contractor / Designer | Current Status | Value (SAR) | Category | Risk Title | Description | Evidence / Data | Probability (1-5) | Impact (1-5) | Score | Rating | Response | Mitigation Plan | Date Identified | Status | Target Date | Notes / Updates | Source
3120-1 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Access & Permits | Egis / MODON | Technical Development Company for Contracting | Open |  | Permits/Stakeholder | Pending SAR Fence Permission Affecting Platform and Canopy Works | The required SAR/fence permission to commence the works inside the designated platform area is still pending. As a result, the Contractor is unable to commence the platform and associated canopy works. Continued delay in obtaining the required permission is affecting the planned sequence of works and may directly impact the project completion date. | Canopy and platform design/details not received from Client; related shop drawings cannot be finalized; associated procurement and construction activities are dependent on the required design information; Client design information remains outstanding. | 5 | 5 | 25 | Very High | Mitigate | Expedite the SAR/fence permission through the Client and relevant authorities. Escalate the matter to project management for immediate resolution. Arrange regular follow-up with the responsible parties and obtain a firm approval/permission date. Prepare manpower, materials, equipment and work fronts in advance so that platform and canopy works can commence immediately once permission is received. Review the programme and implement recovery/acceleration measures if required. | 16/9/2026 | Open |  | SAR/fence permission remains outstanding. Platform and canopy works cannot commence until the required permission is obtained. Continued delay may affect the planned construction sequence and project completion date. | SAR/Fence Permission Correspondence, Client Instructions, RFI/Approval Register, Site Records, Project Scheduledule
3120-2 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Design / Engineering | Egis / MODON | Technical Development Company for Contracting | Open | 9867379 | Design/Technical | Outstanding Canopy and Platform Design Affecting Shop Drawing, Procurement and Construction | The required design/details for the canopy and platform have not yet been provided by the Client. The outstanding design information is preventing the Contractor from finalizing the related shop drawings and progressing associated construction and procurement activities. Continued non-availability of the design information may result in delay to the affected works and potentially impact the overall project completion milestone. | Canopy and platform design/details not received from Client; related shop drawings cannot be finalized; associated procurement and construction activities are dependent on the required design information; Client design information remains outstanding. | 5 | 5 | 25 | Very High | Mitigate | Immediately escalate the outstanding design requirement to the Client/Consultant and request formal issuance of the canopy and platform design. Conduct dedicated coordination meetings to close the outstanding information. Prepare all possible shop-drawing activities in parallel and identify procurement requirements in advance. Once the design is received, prioritize shop-drawing preparation, review/approval, procurement and construction. Assess the schedule impact and develop recovery measures if required. Maintain formal records of all requests and correspondence to protect the Contractor's contractual position. | 16/9/2026 | Open |  | Project is currently ahead of schedule; however, the Client's outstanding canopy and platform design is affecting the finalization of shop drawings and may hold associated procurement and construction activities. Continued delay in receiving the design information may consume available float and potentially impact the overall project completion/handover milestone. | Client/Consultant Correspondence, RFI, Design/Submittal Register, Shop Drawing Register, Procurement Log, Project Schedule
3120-3 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Open |  | Interface/Utilities | Delay in Client Approval for MV Duct Crossings Affecting MV Cable Installation | Client approval is required for the proposed MV duct crossings. If approval is not obtained within the required timeframe, the execution of the MV duct crossings may be delayed, which could subsequently affect MV cable installation and the planned sequence of electrical works. | MV duct crossing proposal/submission pending Client approval; MV cable installation is dependent on completion/availability of the required duct crossings; project is currently ahead of schedule. | 4 | 4 | 16 | High | Mitigate | Expedite Client review and approval of the MV duct crossing proposal. Conduct regular follow-up with the Client/Consultant and obtain formal approval at the earliest. Coordinate the crossing works with civil and electrical teams and prepare resources/materials in advance so that construction can commence immediately after approval. Monitor the activity against the MV cable installation schedule to prevent loss of available float. | 16/9/2026 | Open |  | Project is currently ahead of schedule. However, pending Client approval for MV duct crossings may affect the planned execution of the crossing works and subsequently impact MV cable installation if approval is not received within the required timeframe. | MV Duct Crossing Proposal / Client Correspondence / RFI or Technical Submittal / Project Schedule
3120-4 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Open |  | Authorities / Permits | Delay is recevieng SAR Permit | Affecting Geo technical Report ,Shop Drawing and Backfilling work | Delay in completion date | 4 | 4 | 16 | High |  |  | 2026-05-05 | Close | 2026-06-05 |  |  | Post Treatment
3120-5 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Open |  | Authorities / Permits | Delay is recevieng Tender drawing for platform | Structure Drawing for Platform | Delay in completion date | 3 | 3 | 12 | M12 |  |  | 2026-05-05 | Close | 2026-06-05
3120-6 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Visibility is low due to strong winds and dust. | Vehicle and machinery collisions, falls from high places, and breathing problems. | Severe site hazards, including vehicle and machinery collisions, respiratory damage from inhaled particles, and structural instability from high wind load | 3 | 3 | 12 | M12 |  |  | 2026-08-04 | Close | 2026-08-04 | Suspending high-risk tasks, controlling vehicle movement, and protecting workers.
3120-7 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Found a damaged fire extinguisher in the site office area. | May fail during a fire, can leak harmful chemicals or gas, and it can burst or fly apart. | Complete equipment failure during a fire, sudden rupture or explosion of the pressurized metal container, and delayed evacuation or severe personal injury | 2 | 2 | 10 | L4 |  |  | 2026-08-05 | Close | 2026-08-05 | Finding a damaged fire extinguisher requires immediate removal, clear tagging, and professional servicing
3120-8 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | It was observed that diesel is being stored in plastic containers. | Chemical Breakdown and Leaks, Fuel Contamination, Environmental Spills and Exposure. Fire hazard | Health Risks, Equipment Failure | 2 | 2 | 10 | L4 |  |  | 2026-09-08 | Close | 2026-09-08 | Immediate transfer of the diesel into approved containers and the systematic neutralization of microbial risks
3120-9 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Due to sand storm dust accumulated and poor visibility on site | Visibility & Safety Hazards, Acute Health Risks, Equipment & Asset Damage | Immediate On-Site Consequences (Due to Poor Visibility), Physical Consequences (Due to Accumulated Dust, Health Hazards for Site Personnel, | 2 | 2 | 10 | L4 |  |  | 2026-09-09 | Close | 2026-09-09 | Halt All Mobile Operations: Order an immediate stop to all heavy equipment operation, crane lifting, and vehicle transit. Poor visibility makes navigating the site blind and exponentially increases the risk of collisions or structural strikes. Mandatory Shelter-in-Place: Move all personnel immediately away from open areas. Issue High-Efficiency PPE
3120-10 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Dust created by vehicles moving on project routes | Visibility & Safety Hazards, Acute Health Risks, Equipment & Asset Damage | Health Issues (repiratory), Equipment collsion due low visibility | 3 | 3 | 12 | M8 |  |  | 2026-09-20 | Close | 2026-09-20 | Regular water spraying on vehicle routes
3120-11 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Shade not available for drinking water | Heat Stress to workers on site due improper arrangement of cold water stations. | Heat stress and heat stroke to workers as workers | 3 | 3 | 12 | M8 |  |  | 2026-09-20 | Close | 2026-09-20 | Shaded water station so that water remains cold for long duration for site workers.
3120-12 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Shallow excavation found without safety and warning signages | Visibility & Safety Hazards which could lead in workers and equipment fall in to excavation. | Peronsal injuries and equipment damages | 4 | 4 | 25 | Very High |  |  | 2026-09-24 | Close | 2026-09-24 | posting warning and safety signages to increase the visibility and awareness about riks.
3120-13 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Workers found in equipment working zone | Workers working in machine /equipment working zone are exposed to hit/ struck by the moving machine/ equipment. | Peronal injuries from minor to critical injuries and fatalities | 5 | 5 | 25 | Very High |  |  | 2026-09-24 | Close | 2026-09-24 | Stop movement in man machine/ equioment interface and segrete equipment and man working areas.
3120-14 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | directional signages along with concrete jersey barriers and warning signages and tape were missing | Information signages inncrease Visibility & absence expose workers and equipment to Safety Hazards which could lead in workers and equipment collsion and fall to trenches | Information signages inncrease Visibility & absence expose workers and equipment to Safety Hazards which could lead in workers and equipment collsion and fall to trenches | 5 | 5 | 25 | Very High |  |  | 2026-10-03 | Close | 2026-10-03 | Directional signages along with concrete jersey barriers and warning tape with rope have been provided – New Diversion Road,to ensure safe traffic movement and to guide site vehicles / heavy equipment.
3120-15 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Found equipment operators without PPE complaince | Mandatory PPE non complaince could to several injuries from minor to major. | Mandatory PPE non complaince could to several injuries from minor to major. | 3 | 3 | 12 | M12 |  |  | 2026-10-03 | Close | 2026-10-03 | Wear the mandatory PPE all the time when present on site
3120-16 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Observe Hot Work activity without proper control measure Fire safety | High risk of uncontrolled fire resulted from unavialablity of fire extinguisher | Peronsal injuries and equipment damages | 5 | 5 | 25 | Very High |  |  | 2026-10-10 | Close | 2026-10-10 | Peronsal injuries and equipment damages
3120-17 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Observe site without mandatory PPE complaince | Mandatory PPE non complaince could to several injuries from minor to major. | minor and major injuries | 3 | 3 | 12 | M12 |  |  | 2026-10-11 | Close | 2026-10-11 | minor and major injuries
3120-18 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Observe dust created at temporary vehicles roads due insuffient dust control measures. | Risk of low visibility and respiratory diseases to workers working around | Peronsal injuries and equipment damages | 5 | 5 | 25 | Very High |  |  | 2026-10-18 | Close | 2026-10-18 | Peronsal injuries and equipment damages
3120-19 | 3120 | 3196 | Construction of Passenger Station for SAR Railway Sudair Industrial City | Sudair | Riyadh Region | Government Funded | Construction / Civil Works | Egis / MODON | Technical Development Company for Contracting | Close |  | Safety / Quality | Observe site without mandatory PPE complaince by equipment operator | Mandatory PPE non complaince could to several injuries from minor to major. | minor and major injuries | 5 | 5 | 25 | Very High |  |  | 2026-10-17 | Close | 2026-10-17 | minor and major injuries

## Milestones
Project Name
Item No. | Milestones | Original (Baseline) | Latest | Forecast |  | Days Change
| Contract Duration Current Contract Weeks : 28 of 69 |  | 69.4286 | 69.4286 |  | 0 | 27.8571 | 69.4286
1 | Project Start Milstone | 2026-04-07 | 2026-04-07 | 2026-04-07 | Finish | 0
2 | Mobilization Finish Milestone | 2026-05-06 | 2026-05-06 | 2026-05-06 | Finish | 0
3 | Work Plan and Timeline Milestone | 2026-05-06 | 2026-05-06 | 2026-08-16 | UP | -102
4 | Completion of MV Work | 2027-05-12 | 2027-05-22 | 2027-05-05 | UP | 17
5 | Completion of road and paving works Milestone | 2026-12-06 | 2026-12-06 | 2026-12-31 | UP | -25
6 | Completion of site and platform work Milestone | 2027-07-20 | 2027-07-20 | 2027-08-05 | UP | -16
7 | Completion of finishing works and general site works | 2027-07-20 | 2027-07-20 | 2027-08-06 | UP | -17
8 | Engineering Phase Finish Milestone | 2026-05-06 | 2026-05-06 | 2026-09-21 | UP | -138
9 | Procurment Phase Finish Milestone | 2027-04-15 | 2027-04-15 | 2027-06-09 | UP | -55
10 | Project Finish Milstone | 2027-08-06 | 2027-08-06 | 2027-08-06 | - | 0

## Schedule
Primavera P6 Schedule Status | [9 empty] | Data Date | 2026-10-19
Project Activities Overview
Schedule Statistics |  |  |  |  | Active Schedule Activities
Total Act. | Not Started | In Progress | Completed | % | Active | Ahead | On | Behind | Flag
855 | 586 | 46 | 223 | 26.08% | 10 | 15 | 0 | 22 | -7
Critical Path Activities |  |  | Free Float Management (Total) |  |  |  | Failed Start Activities
|  |  | Greater Than 14 Days |  | Less Than 14 Days
Last Week | This Week | Diff | Last Week | This Week | Last Week | This Week | Last Week | This Week | Flag
0 | 0 | 0 | 53 | 172 | 598 | 570 | 0 | 2 | -2

## EV-Chart Data
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Value |  |  | Gross Paid Value |  |  | Forecast |  |  | Actual/Fcst vs Plan
Month | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | Cum | % | Monthly | C um |  | Month | Cum
2026-04-26 | ` | 0 | 0% |  |  |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 |  |  | 0 | Actuals thru previous month
2026-05-26 | 2034 | 2034 | 0.006147% |  |  |  | 397090 | 397090 | 1.2% | 0 | 0 | 0% | 397090 | 397090 |  | 395056 | 395056
2026-06-26 | 4767 | 6801 | 0.02055% |  |  |  | 980202 | 1377292 | 4.162% | 0 | 0 | 0% | 980202 | 1377292 |  | 975435 | 975435
2026-07-26 | 36612 | 43413 | 0.1312% |  |  |  | 1192785 | 2570077 | 7.767% | 0 | 0 | 0% | 1192785 | 2570077 |  | 1156173 | 1156173
2026-08-26 | 3025382 | 3068795 | 9.274% |  |  |  | 2859151.79 | 5429228.79 | 16.41% | 0 | 0 | 0% | 2859151.79 | 5429228.79 |  | -166230.21 | -166230.21 | Forecast current and future months
2026-09-26 | 7642106 | 10710901 | 32.37% |  |  |  | 482348.68 | 5911577.47 | 17.86% | 0 | 0 | 0% | 482348.68 | 5911577.47 |  | -7159757.32 | -7159757.32
2026-10-26 | 4071913 | 14782814 | 44.67% |  |  |  | 1183964.57 | 7095542.04 | 21.44% | 0 | 0 | 0% | 1183964.57 | 7095542.04 | 21.44% | -2887948.43 | -2887948.43
2026-11-26 | 2368425 | 17151239 | 51.83% |  |  |  | 0 |  |  | 0 | 0 | 0% | 6427021.61 | 13522563.65 | 40.86% | 4058596.61 | 4058596.61
2026-12-26 | 3761619 | 20912858 | 63.2% |  |  |  | 0 |  |  | 0 | 0 | 0% | 7390294.35 | 20912858 | 63.2% | 3628675.35 | 3628675.35
2027-01-26 | 2141463 | 23054321 | 69.67% |  |  |  | 0 | [5 empty] | 2141463 | 23054321 | 69.67% | 0 | 0
2027-02-26 | 1637344 | 24691665 | 74.62% |  |  |  | 0 | [5 empty] | 1637344 | 24691665 | 74.62% | 0 | 0
2027-03-26 | 2104692 | 26796357 | 80.98% |  |  |  | 0 | [5 empty] | 2104692 | 26796357 | 80.98% | 0 | 0
2027-04-26 | 1246419 | 28042776 | 84.74% |  |  |  | 0 | [5 empty] | 1246419 | 28042776 | 84.74% | 0 | 0
2027-05-26 | 955808 | 28998584 | 87.63% |  |  |  | 0 | [5 empty] | 955808 | 28998584 | 87.63% | 0 | 0
2027-06-26 | 1588983 | 30587567 | 92.44% |  |  |  | 0 | [5 empty] | 1588983 | 30587567 | 92.44% | 0 | 0
2027-07-26 | 2381575 | 32969142 | 99.63% |  |  |  | 0 | [5 empty] | 2381575 | 32969142 | 99.63% | 0 | 0
2027-08-26 | 121711 | 33090853 | 100% |  |  |  | 0 | [5 empty] | 121711 | 33090853 | 100% | 0 | 0
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
[14 empty] | 0 | 12303404 | 12303404
3309683
482348.68
0
397090
[8 empty] | 1377292 | [5 empty] | 20912858
2570077
|  | 6881451.01 | 158436 |  |  |  |  | 5429228.79 |  |  | 4070077 |  |  | 0
[8 empty] | 5911577.47 | [5 empty] | 397090
1377292
2570077
|  | 7095542.04 | 166508 | [10 empty] | 5429228.79
5911577.47
11154138.65
13522563.65
20912858
23054321
24691665
|  |  | 5622620.33 | 146227 | [9 empty] | 26796357
28042776
28998584
30587567
32969142
33090853

## Physical-Chart Data
| Baseline Plan |  |  | Revised / Recovery Plan |  |  | Earned Effort % |  |  | Forecast |  |  | Achieved/Fcst vs Plan
Week | Monthly Effort | Cum Effort | Plan Wt.% | MonthlyEffort | Cum Effort | Plan Wt.% | Monthly Wt. | Cum Wt. | Achieved Wt.% | Monthly Wt. | Cum Wt. | Wt.% | Monthly Wt. | Cum Wt.
2026-04-26 | 36221.3 | 36221.3 | 5.673% |  |  |  | 22574 | 22574 | 4.24% | 22574 | 22574 |  | -13647.3 | -13647.3 |  | Actuals thru previous month
2026-05-26 | 10471.3 | 46692.6 | 7.313% |  |  |  | 11000 | 33574 | 8.174% | 11000 | 33574 |  | 528.7 | -13118.6
2026-06-26 | 14207.6 | 60900.2 | 9.538% |  |  |  | 27880 | 61454 | 9.625% | 27880 | 61454 |  | 13672.4 | 553.8
2026-07-26 | 16820.8 | 77721 | 12.17% |  |  |  | 20650 | 82104 | 12.86% | 20650 | 82104 |  | 3829.2 | 4383
2026-08-26 | 62842.3 | 140563.3 | 22.02% |  |  |  | 44752 | 126856 | 19.87% | 44752 | 126856 |  | -18090.3 | -13707.3 |  | Forecast current and future months
2026-09-26 | 54898.5 | 195461.8 | 30.61% |  |  |  | 21939 | 148795 | 23.31% | 21939 | 148795 |  | -32959.5 | -46666.8
2026-10-26 | 49442.2 | 244904 | 38.36% |  |  |  | 17713 | 166508 | 26.08% | 17713 | 166508 | 26.08% | -31729.2 | -78396
2026-11-26 | 40627.8 | 285531.8 | 44.72% |  |  |  | 0 |  |  | 119023.8 | 285531.8 | 44.72% | 78396 | 0
2026-12-26 | 49100.4 | 334632.2 | 52.41% |  |  |  | 0 |  |  | 49100.4 | 334632.2 | 52.41% | 0 | 0
2027-01-26 | 29292.3 | 363924.5 | 57% |  |  |  | 0 |  |  | 29292.3 | 363924.5 | 57% | 0 | 0
2027-02-26 | 23424.4 | 387348.9 | 60.67% | [6 empty] | 23424.4 | 387348.9 | 60.67% | 0 | 0
2027-03-26 | 56271.1 | 443620 | 69.48% | [6 empty] | 56271.1 | 443620 | 69.48% | 0 | 0
2027-04-26 | 56367.4 | 499987.4 | 78.31% | [6 empty] | 56367.4 | 499987.4 | 78.31% | 0 | 0
2027-05-26 | 38590.1 | 538577.5 | 84.35% | [6 empty] | 38590.1 | 538577.5 | 84.35% | 0 | 0
2027-06-26 | 54478.7 | 593056.2 | 92.89% | [6 empty] | 54478.7 | 593056.2 | 92.89% | 0 | 0
2027-07-26 | 44013.6 | 637069.8 | 99.78% | [6 empty] | 44013.6 | 637069.8 | 99.78% | 0 | 0
2027-08-26 | 1398.1 | 638467.9 | 100% | [6 empty] | 1398.1 | 638467.9 | 100% | -2.3192e-11 | -2.3192e-11
UPDATE ONLY YELLOW PORTION FROM PRIMAVERA EXPORT, IF NEEDED, EXTEND YELLOW PORTION BASED ON SCHEDULE.
[6 empty] | 32959.5 | [5 empty] | 0
166508
[5 empty] | 156010 | [6 empty] | 201563.6 | 201563.6
0
[5 empty] | 158436 | [5 empty] | 21939
[7 empty] | 3309683 | 103933.2
[11 empty] | 22574 | 10969.5
[11 empty] | 33574 |  |  |  | 41939
61454
82104
126856
148795
244904
285531.8
334632.2
363924.5
387348.9
443620
499987.4
538577.5
593056.2
637069.8
638467.9

## Testing
Testing and Commissioning
Item | Planned Start Date | Planned Finish Date | Forecast Start Date | Forecast Finish Date | Actual Start Date | Actual Finish Date | % Completed | Open Comments | Closed Comments
Package 1 | 2027-01-19 | 2027-08-06 | 2027-01-25 | 2027-07-27 |  |  | 0% | 0 | 0
Testing and Comissioning | 2027-01-19 | 2027-08-06 | 2027-01-25 | 2027-07-27 |  |  | 0% | 0 | 0
Civil Works | 2027-05-09 | 2027-05-31 | 2027-06-06 | 2027-06-23 |  |  | 0% | 0 | 0
Storm Water Drainage Network | 2027-01-19 | 2027-02-06 | 2027-03-18 | 2027-04-05 |  |  | 0% | 0 | 0
Sewerage Network | 2027-03-14 | 2027-03-31 | 2027-01-25 | 2027-02-13 |  |  | 0% | 0 | 0
Portable Water | 2027-03-22 | 2027-04-08 | 2027-03-28 | 2027-04-14 |  |  | 0% | 0 | 0
Electrical Works | 2027-07-18 | 2027-08-03 | 2027-07-08 | 2027-07-26 |  |  | 0% | 0 | 0
CCTV Works | 2027-07-22 | 2027-08-06 | 2027-07-12 | 2027-07-27 |  |  | 0% | 0 | 0
Package 3 | 2027-01-19 | 2027-08-06 | 2027-01-25 | 2027-07-27 |  |  | 0% | 0 | 0
Testing and Comissioning | 2027-01-19 | 2027-08-06 | 2027-01-25 | 2027-07-27 |  |  | 0% | 0 | 0
Civil Works | 2027-05-09 | 2027-05-31 | 2027-06-06 | 2027-06-23 |  |  | 0% | 0 | 0
Storm Water Drainage Network | 2027-01-19 | 2027-02-06 | 2027-03-18 | 2027-04-05 |  |  | 0% | 0 | 0
Sewerage Network | 2027-03-14 | 2027-03-31 | 2027-01-25 | 2027-02-13 |  |  | 0% | 0 | 0
Portable Water | 2027-03-22 | 2027-04-08 | 2027-03-28 | 2027-04-14 |  |  | 0% | 0 | 0
Electrical Works | 2027-07-18 | 2027-08-03 | 2027-07-08 | 2027-07-26 |  |  | 0% | 0 | 0
CCTV Works | 2027-07-22 | 2027-08-06 | 2027-07-12 | 2027-07-27 |  |  | 0% | 0 | 0
Total | [6 empty] | 0 | 0 | 0
Formulas:
Planned Start Date = [Planned Start Date, row below]
Planned Finish Date = [Planned Finish Date, row below]
Forecast Start Date = [Forecast Start Date, row below]
Forecast Finish Date = [Forecast Finish Date, row below]

## Conclusion (hidden)
تقدم سير مشروع تطوير شبكات البنية التحتية في مدينة سدير للصناعة والأعمال – المرحلة الثانية – الجزء الثاني
معلومات المشروع |  |  |  | نطاق المشروع |  |  |  |  | موقع المشروع
المقاول | شركة تطوير التقنية للمقاولات | الاستشاري | شركة ايجيس السعودية للاستشارات | البند | الكمية الكلية | الكمية المنفذة | الكمية المتبقية | نسبة المنفذ
تاريخ استلام الموقع | 06-01-2026 م | مدة التنفيذ | 18 شهرًا ميلاديًا | أعمال الطرق والرصف (ROD) | 18,252 م | 0 | 0 | -
بداية العقد | من تاريخ استلام الموقع | قيمة العقد (شامل ضريبة القيمة المضافة) | 193,923,948.00 ريال | أعمال شبكة مياة الشرب (WAT) | 18,021 م | 0 | 0 | -
نسبة الإنجاز المخطط له | 0% | نسبة الإنجاز الفعلي | 0.03% | أعمال شبكة المياه المعالجة (TSE) | 16,141 م | 0 | 0 | -
|  | 168629519.99 |  | أعمال شبكة الصرف الصحي (SEW) | 13,040 م | 0 | 0 | -
ملخص جدول الكميات |  |  |  | أعمال شبكة صرف مياه الأمطار (STR) | 13,600 م | 0 | 0 | -
مكونات المشروع |  | التكلفة (غير شامل ضريبة القيمة المضافة) | النسبة الاجمالية | أعمال شبكة الري والمناظر الطبيعية (IRR) | 29,570 م | 0 | 0 | -
أعمال الطرق |  | 88002863.2 | 52.19% | أعمال الشبكة الكهربائية (ELE) | 51,500 م | 0 | 0 | -
شبكة تصريف مياه الأمطار |  | 25408256.59 | 15.07% | أعمال المراقبة بالكاميرات (CCTV) | 125 كاميرا | 0 | 0 | -
شبكة الصرف الصحي |  | 7071026.55 | 4.193% | ملخص التوريدات |  |  |  |  | تقدم أعمال layout
شبكة المياه المعالجة (TSE) |  | 4148179.83 | 2.46% | البند | الكمية الكلية | الكمية المورده | الكمية المتبقية | نسبة التوريد
شبكة مياه الشرب |  | 7780464.9 | 4.614%
الأعمال الكهربائية |  | 20085705.4 | 11.91%
أعمال تنسيق الموقع والري |  | 6827173.87 | 4.049%
أعمال كاميرات المراقبة (CCTV) |  | 9305849.65 | 5.519%
معالم البرنامج الزمني
البند |  | التاريخ حسب الجدول الزمني | ملاحظة
Mobilization Finish Milestone |  | 2026-02-05 | Finish
Baseline Submission Finish Milestone |  | 2026-02-05 | UG | التحديات والعوائق
Technical Submittals Finish Milestone |  | 2026-03-05 | UG | 1-
Quality Lap Finish Milestone |  | 2026-02-05 | Finish | 2-
RBF Finish Milestone |  | 2026-02-05 | Finish | 3-
All Works Finish Milestone |  | 2027-07-05 | UG | 4-
5-
6-
7-